## Slide 1
Agentmux
Platform implementation review
Architecture, migration and phased acceptance
Proposal for Ryan and Nick
October 9, 2026
Notes: Planning and presentation only. No future product functionality or acceptance test is claimed complete. Baseline df46e94570fadf78ef67a75a692dd48b968a10f7, Agentmux 0.32.0. All rearchitecture work belongs on feat/agentmux-platform-rearchitecture. Ryan reviews with Nick and explicitly authorizes merge.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md

## Slide 2
Confirmed product direction
02
Plugin foundation
A protected boot assembly with extensible surrounding services
NATS communication and persistence
Scoped NATS contracts and shared persistence with optional rebuildable SQL views
Client-led work
Existing agent clients lead the workflow; the dashboard shows shared activity
Local and connected teams
Native macOS/Linux, Windows through WSL, self-hosted hubs across organizations
Notes: Accepted direction: a plugin foundation, protected minimal kernel, all internal component communication through NATS, and NATS as preferred shared persistence with optional rebuildable SQL views. Native Windows runtime, hosted service, runtime language, SDK languages and dashboard command scope have not been committed. Detailed stream design, versions, durability and recovery profiles require qualification.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/agentmux-product-architecture-working-brief.md

## Slide 3
Current architecture
03
Agent clients
and terminal
Bash / tmux
harness
Provider processes
and worktrees
Python hub
Federation
extensions
NATS
shared circle
Local dashboard
Board SQLite
Run files and claims
Hub SQLite
Separate ownership and completion signals need explicit migration.
Notes: Verified baseline. Multiple local stores and transport paths coexist. NATS federation is present, but local component communication is not universally NATS. Current federation uses direct broker clients and in-process Python extensions.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/implementation-baseline-review.md
C:/Users/RyanHelms/GitHub/agentmux/agentmux.sh
C:/Users/RyanHelms/GitHub/agentmux/hub/server.py
C:/Users/RyanHelms/GitHub/agentmux/hub/fed/runtime.py

## Slide 4
Proposed product architecture
04
Agent clients
Client integrations
CopilotKit dashboard
NATS communication and shared persistence
AG-UI interface
Plans / tasks
and workspaces
Execution / tools
and domain plugins
Identity / policy
and state owners
Connected
team hubs
Protected kernel publishes permitted status into a separate application scope.
Notes: Approved NATS persistence direction within the proposed product architecture. Ordinary domain plugins own their validated state changes and scoped write contracts. NATS and the operating system are bootstrap infrastructure. JetStream stores authoritative domain change records, KV serves explicitly authoritative configuration/registry plus derived summaries and TTL presence, and Object Store holds immutable-by-policy artifacts where suitable. Optional SQL is a rebuildable read model or cache. No unrestricted direct-storage consumers and no surrounding plugin write into the protected kernel. External tools remain owner implementation details, AG-UI terminates at the interface plugin.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
https://docs.nats.io/learn/key-value/history-and-revisions
https://docs.nats.io/learn/object-store/
https://docs.ag-ui.com/introduction

## Slide 5
Protected kernel boundary
05
Protected boot assembly
Boot and protected-plugin lifecycle
Internal NATS communication
Published kernel status
Surrounding subscribers
Identity, storage, orchestration and domain services live outside this boundary.
Kernel replacement and general external kernel commands remain excluded.
Notes: Accepted minimal kernel: boot, lifecycle of protected plugins, internal communication and status publication. Outside plugins have only permitted subscriptions to published kernel information. No general inbound kernel write interface is approved. Surrounding supervisor owns ordinary plugin lifecycle. Deterministic boot does not depend on an LLM, Jev or identity-provider availability.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/agentmux-product-architecture-working-brief.md

## Slide 6
Nested plugins and scoped context
06
Parent plugin
Parent-owned child
Independent child
PluginContext
Identity, logger, config,
lifecycle and scoped clients
OperationContext
Caller, project, grant,
attempt and deadline
Independent reuse survives parent removal. Concurrent callers never share a mutable “current user.”
Notes: Package relationship, runtime instance ownership and placement are separate declarations. PluginContext carries stable package/instance identity and scoped services. OperationContext carries validated caller/project/task/attempt/grant and deadline. Children inherit allowed defaults, not unlimited authority or a raw service container. Initial trusted native plugins are not hostile-code confinement.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 7
NATS service responsibilities
07
Facility | Planned responsibility | Required distinction
Core request/reply | Queries and live status | Timeout may mean unknown
JetStream | Validated changes and durable history | Commit differs from acceptance
KV and Object Store | Config, summaries and artifacts | Explicit authority and retention
Accounts | Kernel, tenant and partner boundaries | Actual broker enforcement
Leaf topology | Connected sites and execution hosts | Explicit storage and replication
SQL views remain optional and rebuildable. Domain owners control all state changes.
Notes: Approved NATS-first persistence direction. Ordinary domain owners define command validation and state transition rules. JetStream history has its own retention policy, separate from workqueue delivery. KV authoritative config/registry must be distinguished from derived summaries and TTL presence. Object Store does not inherently promise immutable version history; Agentmux must enforce immutable identifiers, digests and access. Core timeout or lost persistence reply may leave an unknown outcome, requiring owner reconciliation. Leaf links do not provide automatic offline persistence or replica freshness.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
https://docs.nats.io/learn/jetstream/advanced-publishing
https://nats.io/blog/nats-server-2.12-release/
https://docs.nats.io/learn/key-value/history-and-revisions
https://docs.nats.io/learn/object-store/
https://docs.nats.io/learn/jetstream/retention-policies
https://docs.nats.io/learn/topologies/leaf-nodes
https://docs.nats.io/learn/jetstream/publishing
https://docs.nats.io/learn/jetstream/mirrors-and-sources
https://docs.nats.io/learn/jetstream/get-direct

## Slide 8
Shared persistence and data placement
Store | Planned contents | Authority and lifecycle
JetStream | Task, attempt and delegation changes | Owner-validated durable history
KV | Configuration and plugin registry | Authoritative scoped records
KV | Task summaries and presence | Derived state and TTL freshness
Object Store | Digests, evidence and larger artifacts | Immutable identifiers where suitable
Optional SQL | Search indexes and reporting views | Rebuildable queries and caches
Each domain declares retention, access and restore behavior.
Presence expiry never releases an assignment.
08
Notes: Approved data-placement direction, implementation remains paused. JetStream is the preferred shared persistence for validated domain change records. KV can be authoritative for configuration/registry if its scoped owner specifies revision/CAS, history and durability behavior; task summaries and presence are derived. TTL is freshness information, not execution or reassignment authority. Object Store stores artifact payloads when suitable, while immutable identifiers/digest checks and access are Agentmux policies because the store API supports mutable objects and deletion. SQL indexes and caches are optional projections rebuildable from retained authoritative evidence, not an independent state writer. A projection can only rebuild within the retained history/snapshot recovery contract.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
https://docs.nats.io/learn/key-value/history-and-revisions
https://docs.nats.io/learn/object-store/
https://docs.nats.io/learn/jetstream/retention-policies

## Slide 9
Domain-owned commits and read models
Scoped command
through NATS
Domain owner
validates transition
JetStream
authoritative record
Derived KV / optional SQL
with revision and freshness
One-stream atomic batch
Available since NATS Server 2.12.
Pin and prove the server / SDK combination.
Cross-stream, hub and tool effects need reconciliation.
Only the scoped owner can authorize execution. A stale view cannot.
09
Notes: Approved persistence direction, detailed implementation remains proposed. Commands enter via scoped NATS owner contracts with durable operation identity, canonical payload hash and expected record version. The ordinary domain owner checks caller, current authority, grant and a conditional write before granting execution. Reusing an identity with a different payload is a conflict. Prefer one complete transition record including provenance and recoverable effect intent. Atomic batch publish was introduced in NATS Server 2.12: within one stream messages are staged and all consistency checks must pass before the batch commits. Pin and prove server/SDK behavior, stream configuration, limits, retries and crash boundaries. Fast-ingest batching is distinct and cannot substitute for atomic batching. This is not a transaction across streams, KV buckets, hubs, object uploads, read-model updates or external tools. Lost commit acknowledgement is an unknown outcome reconciled by the same operation identity and owner state before retrying effects. Persist duplicate outcomes and unresolved reservations beyond the agreed reconnect/restore horizon and broker deduplication window. History replay only rebuilds views and cannot replay external actions. Read models carry revision/freshness and cannot authorize execution. Commit and consumer acknowledgement are separate from domain acceptance.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
https://docs.nats.io/learn/jetstream/advanced-publishing
https://nats.io/blog/nats-server-2.12-release/
https://docs.nats.io/learn/jetstream/publishing
https://docs.nats.io/learn/key-value/history-and-revisions
https://docs.nats.io/learn/jetstream/get-direct

## Slide 10
Persistence across disconnects and recovery
Origin domain
Task and acceptance owner
Execution domain
Attempt and evidence owner
Scoped NATS link
Durable domain history
Retain history separately from workqueues.
Record reservation and reconciliation identity.
Restore ownership with verified evidence.
Rebuildable local views
Show replica revision and freshness.
Recover gaps from retained history / snapshots.
Test partitions, storage loss and backup restore.
Lost acknowledgements retain uncertainty. Reconnect reconciles the same delegation.
10
Notes: Each offline-capable hub needs its own independently persistent JetStream domain, explicit subject access and deliberate mirror/source or application reconciliation contracts. A leaf link alone is not a storage replication or freshness guarantee. Origin owns task acceptance and receiver owns execution. An accepted or acceptance-unknown reservation remains reserved across disconnect; no blind timeout redispatch. Receiver may continue within its grant and reconcile the same delegation on reconnect. Expiry blocks new effects but preserves authenticated historical evidence. Domain history must survive separate workqueue acknowledgement/removal rules. Snapshot manifests bind schema versions, record/artifact identities and stream cursors. Missing ranges, invalid digests and corrupt checkpoints cause explicit repair/readiness failure, never an apparently empty project. Recovery tests include lost commit ack, stale read models, retention gaps, quorum/disk failure, backup restore, object digest verification and SQL/KV projection rebuild. Mirrors and backups require a pinned-version operational test profile and do not establish global multi-writer task authority. No shared transaction is promised between domains or external tool effects.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
https://docs.nats.io/learn/topologies/leaf-nodes
https://docs.nats.io/learn/jetstream/retention-policies
https://docs.nats.io/learn/jetstream/publishing
https://docs.nats.io/learn/jetstream/mirrors-and-sources
https://docs.nats.io/learn/jetstream/get-direct

## Slide 11
Developer workflow before and after
11
Today
Launch a pane
Send prompts
and inspect output
Update several
work records
Review files
and approvals
Proposed
Request work
in a client
Track plan
and scoped attempts
Inspect evidence
and conversations
Accept result
at the origin
Client and dashboard connections may close while durable work continues.
Notes: Before workflow is a summary of existing separate harness/task/run steps. After is the proposed complete reference workflow. Existing external client sessions and Agentmux-owned workers are different resources. Publishing and merging require explicit authority.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/implementation-baseline-review.md

## Slide 12
Concurrent users and workspaces
12
Developer A
Developer B
Project A scope
Project B scope
Owned attempts
and worktrees
Owned attempts
and worktrees
Validated caller and grant on every operation
P04 also qualifies worker OS/container/host separation for mutually untrusted task code.
Notes: Proposed identity/workspace model. Isolation must apply to reads, subscriptions, artifact access, secret resolution and commands. Worktree isolation separates Git state but does not by itself provide process security. Shared work requires explicit coordination and ownership.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 13
Federated ownership
13
Origin hub
Task and acceptance owner
Receiving hub
Delegated execution owner
Scoped NATS link
Local execution host
with declared offline grants
Offer and grant
Progress and evidence
Origin acceptance
A result submission preserves executor, task version, artifact digest and provenance.
Notes: Origin owns task and final result acceptance. Receiver owns delegated execution. The proposed launch includes independently administered organizations. A scoped NATS link permits only explicitly exported services/data. Transitive connectivity provides no implicit access. Local and team persistence/failure behavior must be tested.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json
https://docs.nats.io/learn/topologies/leafnodes

## Slide 14
Disconnected work stays reserved
14
Offer
Accepted
and reserved
Execution
Acceptance unknown
Reply lost
Disconnected
Reservation retained
Result submitted
Origin reviews
A connectivity timeout never authorizes reassignment.
Receiver may continue within its grant and reconcile the same delegation after reconnect.
Expired grants block new effects. Historical results remain available.
Notes: No automatic timeout edge from accepted or acceptance-unknown delegation to execution on another hub. Lost acceptance reply can hide a successful acceptance. Receiver may continue within its offline grant. Reassignment is explicit, records prior attempt and cannot guarantee reversal of external effects. Revocation cannot instantly stop an isolated machine.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 15
Authorization at the work owner
15
Validated caller
Broker subject
permissions
Authoritative owner
checks and transition
Revalidation
Current grants, task version, approval and artifact identity
Policy outcomes
Allow, hard deny or review required. Approval cannot override a hard denial.
Launch isolates worker code. P14 separately qualifies untrusted third-party plugins.
Notes: Proposed two-layer enforcement. Broker permissions limit message/API reach. Authoritative service validates actor, operation scope, policy, task version, approval and state. NATS possession or an agent claim alone cannot grant domain authority. Trusted plugins initially can still abuse OS privileges, so scope claims must match that trust assumption.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 16
AG-UI dashboard projection
16
NATS records
and events
Authorized
interface plugin
AG-UI
CopilotKit dashboard
Plans and tasks
Work, agents and evidence
Agent conversations
Snapshots and ordered updates
Reconnect and missing-history recovery
Atoms, molecules, organisms, templates
Dashboard actions remain a P00 scope decision. Any enabled command returns to its owner.
Notes: Accepted UI direction and proposed mapping. NATS retains internal communication and authoritative ownership. AG-UI is the UI-facing event contract. CopilotKit supplies interface facilities. Snapshot/revision/replay authorization must be implemented by the platform. Display only supported client events, authored plans/messages and emitted summaries; no claim of private model reasoning access.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
https://docs.ag-ui.com/concepts/events
https://docs.ag-ui.com/concepts/state
https://docs.copilotkit.ai/
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/agentmux-product-architecture-working-brief.md

## Slide 17
Optional Jev decision pipeline
17
Exact eligibility
and export policy
Bounded evidence
and versioned question
Optional Jev
decision
Deterministic policy
and revalidation
Authorized owner
executes or abstains
Decision and
outcome evidence
Jev advice cannot grant permissions, release reservations or accept a result.
Notes: Proposed optional semantic service. Exact eligibility and data export checks occur before hosted inference. Jev supports bounded decisions; it is not used to generate arbitrary summaries or code. Policies revalidate current state and grants before any command. Abstention, unavailable provider, invalid output, stale source and uncertain billing remain explicit. Boot and ordinary orchestration work without Jev.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/agentmux-jev-integration-report.md
https://docs.typesafe.ai/introduction

## Slide 18
Measuring token and cost savings
18
Comparison | Measure on equivalent tasks
Existing workflow | Accepted outcomes, engineer time, tokens and total cost
Jev tools | Add Jev cost, retries, failed calls and cache changes
Jev tools plus skills | Add trigger accuracy, evidence retention and rework
Proposed activation threshold
At least 10% lower total cost per accepted outcome, with approved quality limits
Fewer downstream tokens can still cost more when prompt caching deteriorates.
Notes: No measured Agentmux product savings are claimed. Earlier offline scenario math uses illustrative LLM prices/volumes and shows a cache-loss counterexample. P08 proposes independent comparisons of baseline, Jev tools and tools+skills, with final untouched cases. Proposed default-activation target is >=10% lower total cost per accepted outcome and <=2 percentage-point accepted-outcome degradation, with uncertainty reported. These values need approval and adequate sample sizes. Classifier thresholds are definition/risk-specific. Pilot productivity comparisons use matched baseline tasks and report time to first accepted change, engineer active minutes, elapsed time, review iterations, reopened work, escaped defects, recovery effort and cost per accepted outcome, with sample size and task mix.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/jev-efficiency-scenarios.mjs
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 19
Portable Jev and Agentmux skills
19
Portable jev plugin: 13 proposed skills
Bounded classification, source inspection, evidence checks and context selection
Agentmux integrations: 10 proposed skills
Task and delegation advice using scoped hub contracts
Industrial packages: 3 proposed skills
Engineering evidence and diagnostics within declared domain permissions
Shared runtime, distinct skill triggers, host-specific packaging and actual-host evaluation.
Notes: The skill-suite proposal contains 13 general, 10 Agentmux-specific and 3 industrial skill proposals, totaling 26. Names, triggers and defaults remain for discussion and evaluation. They are not 26 installed skills. General skills are useful independently of Agentmux; Agentmux skills bind to authorized hub contracts; domain skills ship in industrial packages. CLI/MCP runtime portability does not imply identical hooks, compaction or event capture on each host.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/jev-plugin-skill-suite-proposal.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 20
Industrial extension packages
20
General orchestration contracts
Industrial engineering package
Guidance, workflows and evidence rules
Vendor and tool children
CODESYS / Siemens / Rockwell
Declared execution host and tool versions
Read, validate and mutate operations have separate permissions and evidence
Notes: Industrial controls is an optional domain layer, not a specialization of the general kernel. Preserve current operational modules and explicitly select supported vendor/tool/host versions. CODESYS, Siemens and Rockwell are vendor families to scope, not claims of complete current automation. Simulated transport tests do not qualify device writes. Unknown external outcome prevents blind retries.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/implementation-baseline-review.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 21
Migration with one authoritative writer
21
Inventory
and snapshot
Import into NATS
and reconcile
Compare
read-only views
Switch new
operations
Preserved evidence
Task IDs, run history, approvals and artifacts
Pending delivery and delegation state
Dirty worktrees and unmerged branches
Legacy retirement follows parity, migration rehearsal and an explicit recovery decision.
Notes: Proposed cutover: inventory source state and semantics, versioned export/import, read-only comparisons, writer cutover, recovery proof then explicit retirement. Preserve stable IDs and evidence, pending messages, dirty worktrees and unmerged branches. Never replay historical completed commands or assume external side effects reverse with local rollback.
Approved persistence direction: migrate each domain to one authoritative NATS-backed writer. Preserve historical IDs, versions, approvals, reservations and evidence, then rebuild derived KV/SQL views. Test catch-up and rollback against the frozen snapshot and active-work ownership. Never permit uncontrolled dual writers.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/implementation-baseline-review.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 22
Phase acceptance and evidence
22
Implement
Verify criteria
Independent
review
Authorize
advancement
Evidence belongs to an exact revision
Source, contracts, environments, commands, results and rollback rehearsal
Unverified stays visible
A skipped environment or agent “done” message does not pass a gate
Merge and release require the separate Ryan/Nick review and Ryan’s explicit authorization.
Notes: Proposed gate record includes phase/revision, commit, dependency/config/schema versions, criterion IDs, environment/dataset, commands/exit codes, artifacts, fault tests, limitations, rollback rehearsal, independent reviewer and authorized advancement. Each phase depends on accepted predecessor. Skips and mock-only substitutes are gaps. Material changes invalidate affected evidence. Waivers cannot change accepted authority/security/kernel/reservation/merge invariants.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 23
Proposed delivery sequence
23
Phases | Primary outcome
P00–P04 | Decisions, contracts, boot, plugins and scoped ownership
P05–P07 | Local workflow, supported clients and dashboard
P08–P09 | Evaluated Jev services and portable skills
P10–P12 | Connected hubs, industrial packages and release evidence
P13–P14 | Remaining experiments and sandbox qualification
Launch recommendation: P00–P12. No dates or staffing commitments are implied.
Notes: P00-P12 is the proposed first-release sequence, including initial-release cross-organization federation. P13 preserves remaining evaluated Jev/skill proposals, and P14 qualifies sandboxing later. This release split is proposed, not an approved scope reduction. All phases promote sequentially. Independent preparation may overlap only within approved contracts. Relative sizes are not dates.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 24
P00 Scope and baseline
24
An approved implementation contract with no unresolved decision hidden in code.
Work
Confirm workflow, runtime and support choices.
Detail approved NATS persistence and recovery.
Acceptance gate
Reviewed plan and traceability.
Ryan authorizes implementation.
P00-AC01 through P00-AC04
Owner: Product + architecture
Notes: PROPOSED PHASE. Full authoritative phase definition follows. No acceptance criterion is claimed passed. Implementation remains paused pending Ryan's explicit authorization.
P00: Scope, baseline, and architecture decisions
Status: proposed
Outcome: An approved implementation contract with no unresolved decision hidden in code.
Accountable function: Product + architecture
Relative size: M (complexity, not calendar duration)
Dependencies: none
Work packages
1. Freeze df46e94570fadf78ef67a75a692dd48b968a10f7 as the behavioral comparison baseline and inventory every CLI verb, dashboard view, protocol, state store, integration, and evaluation.
2. Resolve launch workflow, dashboard controls, language/runtime and initial SDKs, storage topology, NATS account/domain layout, supported OS/tool versions, initial scale, identity enrollment, and provider/data policy.
3. Reproduce or explicitly scope the previously reported federation correctness defects. Turn each into a regression case owned by the replacing phase.
4. Approve versioned state machines, authority boundaries, plugin manifest/context schemas, migration ownership, and the requirement-to-phase matrix.
5. Record approved storage direction STATE-01. Select JetStream authority boundaries, retention/checkpoint policy, replication/sync profiles, broker/API access scopes and supported SDK versions. Keep any proposed authoritative SQL exception visible for review.
Acceptance criteria
P00-AC01: Every accepted user decision and all existing functional groups have a named owner phase and verification scenario.
P00-AC02: Ryan and Nick review the plan and decision log. Ryan explicitly authorizes implementation before P01 starts.
P00-AC03: All P01–P04 blocking choices have recorded alternatives, rationale, and consequences. Later choices have a deadline before their owning phase.
P00-AC04: Baseline checks identify passes, failures, missing environments, and historic-only claims separately.
Verification
1. Review the traceability matrix and inspect contracts together.
2. Run existing relevant suites on supported environments and reproduce the four reported crash/dispatch defects with isolated fixtures.
3. Record the exact commit, tools, fixtures, and results. Review missing environments as gaps, not passes.
Required evidence
- Approved plan revision and decision log
- Baseline behavior inventory and defect fixtures
- Compatibility and capacity profiles
Rollback / containment: Planning only. Preserve current checkout behavior and the existing review history.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 25
P01 Contracts and verification
25
Contracts and failure scenarios can be tested before business plugins grow.
Work
Repair inherited correctness blockers.
Prove NATS commit boundaries and two-hub reservations.
Acceptance gate
Independent clients interoperate.
Required regressions and governance checks pass.
P01-AC01 through P01-AC05
Owner: Architecture + quality
Notes: PROPOSED PHASE. Full authoritative phase definition follows. No acceptance criterion is claimed passed. Implementation remains paused pending Ryan's explicit authorization.
P01: Executable contracts, baseline repairs, and verification
Status: proposed
Outcome: Contracts and failure scenarios can be tested before business plugins grow.
Accountable function: Architecture + quality
Relative size: L (complexity, not calendar duration)
Dependencies: P00
Work packages
1. Publish language-neutral command/event schemas and compatibility rules with organization, project, task, delegation, attempt, operation, schema version, and trace identifiers.
2. Create reusable contract fixtures and controllable fake workers/providers plus real NATS integration environments for CI.
3. Specify lifecycle, delivery acknowledgment, idempotency, deadline, cancellation, approval, and unavailable/unknown result semantics.
4. Establish per-phase evidence records, dependency gates, migration fixtures, and security/quality regression jobs.
5. Build an early two-hub contract spike with separate broker accounts and a leaf link. Exercise lost acceptance acknowledgment and reservation reconciliation before the later production federation phase.
6. Repair the six known baseline blockers after implementation approval, with focused regressions and truthful governance evidence. This prevents existing violations from blocking every later phase while waiting for the new federation layer.
7. Build a bounded NATS persistence spike before production storage code: one owning task record, persistent operation identity, conditional competing writes, complete provenance/effect intent, lost acknowledgments and replay. Exercise single-record commits and any required atomic batch inside one stream.
Acceptance criteria
P01-AC01: Two independently implemented test clients exchange valid requests and reject incompatible or malformed envelopes.
P01-AC02: Fixtures cover duplicate, delayed, out-of-order, unauthorized, canceled, timed-out, and replayed messages without conflating execution with delivery.
P01-AC03: A failing predecessor gate prevents promotion. Waivers cannot bypass accepted ownership or security invariants.
P01-AC04: CI captures exact versions and logs without recording credentials or private model reasoning. Known baseline blockers are repaired or disproved with evidence, and the required repository governance gate passes before P02 progression.
P01-AC05: Two language clients pass the NATS storage fixtures on pinned server/client versions: competing revisions admit one transition, partial atomic batches leave no partial record set, and lost acknowledgments reconcile the same operation. Unsupported cross-stream or external-effect transactions are rejected or handled by an explicit recovery contract.
Verification
1. Run schema/contract suites in macOS, Linux, and WSL test jobs.
2. Break one contract fixture and one phase gate deliberately and confirm the pipeline refuses promotion.
3. Exercise a real broker restart and reconnect in the harness.
4. Run FAIL-42, FAIL-43 and FAIL-47 with real JetStream. Record which server/API/SDK capabilities provide each guarantee, including batch behavior and authoritative read freshness.
Required evidence
- Contract version 1 fixtures
- Failure injection harness
- CI gate and compatibility reports
- NATS storage capability report and transaction-boundary fixtures for STATE-01
Rollback / containment: Keep the new test path isolated from the legacy runtime. If a baseline repair is reverted, reopen its finding and invalidate the affected regression and phase-gate evidence.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 26
P02 Protected boot and NATS
26
A local installation boots deterministically with protected kernel plugins.
Work
Bootstrap broker access and protected plugins.
Pin persistence profiles, versions and recovery behavior.
Acceptance gate
Boot without hosted inference.
Outside plugins cannot write into the kernel.
P02-AC01 through P02-AC04
Owner: Runtime + messaging
Notes: PROPOSED PHASE. Full authoritative phase definition follows. No acceptance criterion is claimed passed. Implementation remains paused pending Ryan's explicit authorization.
P02: Protected boot and the NATS foundation
Status: proposed
Outcome: A local installation boots deterministically with protected kernel plugins.
Accountable function: Runtime + messaging
Relative size: L (complexity, not calendar duration)
Dependencies: P01
Work packages
1. Implement a minimal launcher that establishes the configured NATS substrate and loads the fixed protected boot assembly.
2. Implement boot, protected-plugin lifecycle, protected internal communication, and deliberate publication of kernel status.
3. Separate protected internal subjects/accounts from exported information and surrounding application services.
4. Provide readiness snapshots, bounded startup/shutdown, broker recovery, basic installer/doctor skeleton, and local bootstrap diagnostics.
5. Provision the approved local file-backed JetStream profile and team connection profile with explicit storage paths, limits, health and domain settings. Business state ownership stays in surrounding plugins.
Acceptance criteria
P02-AC01: macOS, Linux, and WSL installations boot without an LLM or hosted Jev connection.
P02-AC02: An outside plugin can subscribe only to permitted kernel information and cannot publish commands or writes into the kernel.
P02-AC03: Bad configuration, occupied ports, unavailable broker, and failed protected plugin produce actionable bounded failures.
P02-AC04: Surrounding plugin failure does not corrupt boot state. Ordinary runtime communication uses NATS after bootstrap.
Verification
1. Capture broker traffic and audit permissions while running normal and unauthorized clients.
2. Cold-start and restart each platform. Kill NATS and one protected plugin at controlled points.
3. Verify late subscribers receive a consistent readiness snapshot and updates.
Required evidence
- Boot and shutdown matrix
- Kernel publication contract and permission tests
- Bootstrap recovery guide
Rollback / containment: Disable the new runtime entrypoint and retain the old launcher. No legacy data conversion yet.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 27
P03 Plugin framework and context
27
A third-party author can build a compatible trusted plugin without changing the kernel.
Work
Implement package lifecycle and both child modes.
Supply scoped contexts and interoperable SDKs.
Acceptance gate
Children cannot widen authority.
Two languages pass shared contracts.
P03-AC01 through P03-AC05
Owner: Plugin platform + SDK
Notes: PROPOSED PHASE. Full authoritative phase definition follows. No acceptance criterion is claimed passed. Implementation remains paused pending Ryan's explicit authorization.
P03: Plugin framework, nested packages, and inherited context
Status: proposed
Outcome: A third-party author can build a compatible trusted plugin without changing the kernel.
Accountable function: Plugin platform + SDK
Relative size: XL (complexity, not calendar duration)
Dependencies: P02
Work packages
1. Implement manifest validation, dependency/version resolution, lifecycle supervision, package provenance, configuration schemas, and contribution registration.
2. Support independently reusable and parent-owned child packages, separately declaring runtime instance ownership and placement.
3. Inject PluginContext and per-call OperationContext. Supply identity, scoped logger, tracing/metrics, config, lifecycle, clock, and approved NATS service clients.
4. Add declared storage, artifacts, secrets, workspace, process, policy, and decision handles without sharing raw service implementations or an unrestricted container.
5. Build starter SDKs and conformance tooling in at least two selected languages. Provide install/upgrade/disable/uninstall and drain behavior.
Acceptance criteria
P03-AC01: Both child package modes install and activate correctly. Removing one parent retains independent children used elsewhere.
P03-AC02: Two concurrent users cannot overwrite an ambient current-user/current-project value. A child cannot widen its grant or forge logger identity.
P03-AC03: Dependency cycles, missing versions, partial initialization, and stale handles fail deterministically and clean up resources.
P03-AC04: A plugin in each selected language passes the same contract fixtures and interacts with another plugin over NATS.
P03-AC05: The protected kernel has no replacement option in package management. Trusted native code is accurately documented as unsandboxed.
Verification
1. Run an independent author exercise using only published SDK/docs.
2. Test lifecycle/resource leaks, dependency failure, configuration precedence, version skew, and upgrades with active operations.
3. Inspect NATS traces and execute negative tests at remote resource owners.
Required evidence
- Plugin manifest and SDK reference
- Conformance matrix and author tutorial
- Nested-package/lifecycle test report
Rollback / containment: Pin the last working package set, drain active work, and restore compatible configuration. Never silently downgrade incompatible storage.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 28
P04 Identity, state and workspaces
28
Multiple users and projects share a hub with explicit authority and durable ownership.
Work
Persist scoped state through NATS owners.
Qualify worker isolation, replay and projection rebuilds.
Acceptance gate
Cross-scope writes fail.
Lost replies and stale views cannot grant new work.
P04-AC01 through P04-AC07
Owner: Security + data platform
Notes: PROPOSED PHASE. Full authoritative phase definition follows. No acceptance criterion is claimed passed. Implementation remains paused pending Ryan's explicit authorization.
P04: Identity, projects, durable state, and workspaces
Status: proposed
Outcome: Multiple users and projects share a hub with explicit authority and durable ownership.
Accountable function: Security + data platform
Relative size: XL (complexity, not calendar duration)
Dependencies: P03
Work packages
1. Implement human, device, service, and plugin identities, enrollment/revocation, organization/project membership, permissions, approvals, and audit outside the kernel. Distinguish allowed, denied, and review-required actions; ordinary approval cannot override a hard denial.
2. Implement NATS-backed persistence through ordinary domain-owner plugins. Commit validated state changes, provenance, operation outcomes and recoverable outgoing intent together in the owning JetStream record or qualified same-stream batch. Provide KV configuration/current views, Object Store evidence references, scoped access, retention and backup/restore.
3. Provide scoped workspace/Git/worktree management, configuration, connection/secret references, quotas, and resource reservations.
4. Provide local single-user defaults and self-hosted identity configuration using the same contracts.
5. Implement the approved worker execution profile so mutually untrusted task code cannot share unrestricted access to another user's files or credentials. Qualify OS/container/host separation independently of the later third-party-plugin sandbox.
6. Build optional SQLite/SQL query indexes and caches from committed records and versioned checkpoints. Record consumed sequence and schema version, expose freshness, rebuild without commands or side effects, and prevent projections from granting execution or approval.
Acceptance criteria
P04-AC01: Cross-user/project/organization negative tests deny unauthorized commands, subscriptions, files, artifacts, and secret resolution.
P04-AC02: A committed NATS record or qualified same-stream batch preserves the state change, provenance and recoverable outgoing intent. Crashes before or after commit, publication or acknowledgment converge to the recorded operation without a second business effect.
P04-AC03: Duplicate delivery with the same operation ID and payload hash returns the existing outcome without allocating a second workspace or task. Reusing an operation ID with a different payload is rejected as a conflict.
P04-AC04: Backup/restore preserves ownership and result provenance. Migration fences the former writer, preserves stable IDs, dirty worktrees and unmerged branches, and verifies imported records before admitting new writes.
P04-AC05: Node revocation and secret rotation have tested online behavior and explicit offline limits.
P04-AC06: Deleting or corrupting an optional SQL index or derived KV view is recoverable from retained authoritative records and validated checkpoints. Rebuild preserves authorized results and cursors, detects missing history, and cannot launch work or replay external effects.
P04-AC07: Task history and reservations survive work-queue acknowledgment and presence expiry. Storage/API permissions prevent unauthorized reads and raw writes. Stale views expose their revision and cannot authorize a claim, approval or reassignment.
Verification
1. Run the permission matrix against application owners and real broker accounts. Run an adversarial worker that attempts cross-project file, process, network, and credential access under the supported execution profile.
2. Inject failures before/after commit and publish acknowledgment, exhaust disk/quota, and restore from backup.
3. Run concurrency tests against every supported storage provider. Reject a provider that lacks required guarantees.
4. Run FAIL-42 through FAIL-48, delete projections, corrupt a checkpoint, simulate lagging views and test direct broker APIs. Verify snapshots and retained history form a complete recovery chain.
Required evidence
- Threat model and permission matrix
- Storage capability and migration contracts
- Recovery and isolation reports
- Authoritative record, KV and object inventory with retention, checkpoint and projection rebuild evidence
Rollback / containment: Quiesce and fence writers, retain verified backups and record the authority-switch revision. A return to SQLite authority requires an explicit compatible reverse migration and reconciliation of all NATS-era writes; reverting binaries or restoring an old database alone cannot reopen admission.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 29
P05 Local orchestration
29
A developer can finish a reviewable software task through durable coordinated work.
Work
Implement plans, assignments and supervised attempts.
Deliver software changes with reviewable evidence.
Acceptance gate
Complete reference workflow.
Acceptance requires owner review, not terminal text.
P05-AC01 through P05-AC05
Owner: Orchestration + developer workflow
Notes: PROPOSED PHASE. Full authoritative phase definition follows. No acceptance criterion is claimed passed. Implementation remains paused pending Ryan's explicit authorization.
P05: Local orchestration and evidence-based completion
Status: proposed
Outcome: A developer can finish a reviewable software task through durable coordinated work.
Accountable function: Orchestration + developer workflow
Relative size: XL (complexity, not calendar duration)
Dependencies: P04
Work packages
1. Implement project plans, tasks, dependencies, boards, role/agent/team definitions, assignment, run/attempt state, claims, resource scheduling, and explicit acceptance.
2. Implement supervised workers, session resume capability, isolated worktrees, tool calls, messages, handoffs, progress, conversation records, artifacts, validation, and review workflows.
3. Separate provider/process exit, reported completion, verified evidence, and owner acceptance. Model cancellation-requested, canceled, failed, and unknown states.
4. Port existing journal/notice/dead-letter, search/knowledge, code sharing, cost/resource, and orchestration evaluation behavior behind plugins.
5. Produce a software-change workflow from request through test evidence and a reviewable diff/PR proposal. Publishing and merging follow explicit permissions.
6. Preserve epics, sprints, ADR/capability proposal records, WIP/readiness gates, notifications, objections, and independent reviewer policy. Bind reviews to immutable repository/commit/artifact identities across multiple repositories.
7. Persist orchestration transitions through the NATS-owning domain contracts. Drive dispatch and result publication from recoverable committed intent, and keep queue acknowledgment separate from task completion and origin acceptance.
Acceptance criteria
P05-AC01: A complete fixture workflow creates a plan, delegates tasks, executes in isolated workspaces, validates the result, and returns reviewable evidence.
P05-AC02: Two developers working on different or shared projects do not steal each other's claims, sessions, workspaces, or tool credentials.
P05-AC03: No task becomes accepted from terminal text, process exit, or a worker's self-reported done event alone.
P05-AC04: A crashed or disconnected worker leaves a recoverable known or explicitly unknown attempt. Retry preserves the prior attempt and its effects.
P05-AC05: Every P05-owned legacy functional group has parity evidence or an explicit replacement and data migration decision. Later client, dashboard, federation, and domain groups have an owned inventory and migration plan, with parity gated in their own phases. Changed artifacts invalidate bound approvals, and migration preserves distinct board, run, hub-work, and shared-board identities.
Verification
1. Run normal, failure, retry, cancellation, resume, parallel-team, cross-repo, and swarm-style scenario suites.
2. Inject crash windows around work attribution and result publication identified in the repository analysis.
3. Use real CLI worker smoke tests plus deterministic fake workers for exhaustive state transitions.
Required evidence
- End-to-end workflow recording
- Completion/ownership invariant report
- Legacy parity and migration checklist
Rollback / containment: Route new tasks back to the legacy path only after draining or explicitly reconciling active attempts. Never run both paths as writers for one task.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 30
P06 Supported client entry points
30
Developers use Agentmux from their preferred supported client.
Work
Package CLI/MCP integrations for selected hosts.
Declare control, event, resume and hook capabilities.
Acceptance gate
Actual-host reference workflows pass.
Unsupported capabilities remain explicit.
P06-AC01 through P06-AC04
Owner: Integrations + developer experience
Notes: PROPOSED PHASE. Full authoritative phase definition follows. No acceptance criterion is claimed passed. Implementation remains paused pending Ryan's explicit authorization.
P06: Agent-client entry points and portable tooling
Status: proposed
Outcome: Developers use Agentmux from their preferred supported client.
Accountable function: Integrations + developer experience
Relative size: L (complexity, not calendar duration)
Dependencies: P05
Work packages
1. Provide stable CLI and MCP interfaces generated from declared command contracts, with discoverable resources and error semantics.
2. Package and test integrations for Claude Code, Codex CLI, Pi, and Claude Desktop using each host's documented capabilities.
3. Distinguish external client sessions submitting work from Agentmux-managed worker sessions. Publish coverage for events, controls, resume, hooks, and compaction.
4. Add setup, credential references, diagnostics, install checks, and client-specific documentation without silently replacing user configuration.
5. Inventory and qualify existing Grok/provider authentication methods and any Bedrock compatibility path. Migrate GitHub and Jira/Confluence workflows as tool plugins with explicit writes and credentials.
Acceptance criteria
P06-AC01: Each supported client can submit a task, inspect progress/evidence, participate in required approvals, and retrieve the result.
P06-AC02: Unsupported event capture, cancellation, or compaction reports an explicit capability limit instead of simulating success.
P06-AC03: Closing the originating client or observer does not duplicate or implicitly terminate durable work.
P06-AC04: Fresh-user install and uninstall preserve unrelated client settings and secrets.
Verification
1. Execute the same reference workflow on every pinned client version in the support matrix.
2. Test reconnect, authentication expiry, missing tool, malformed MCP request, and client shutdown.
3. Review provider commercial integration terms before promising a supported paid distribution.
Required evidence
- Actual-host compatibility matrix
- CLI/MCP reference and setup guides
- Per-client workflow results
Rollback / containment: Disable only the affected adapter and preserve the underlying task state and alternate CLI access.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 31
P07 AG-UI and Atomic Design
31
Authorized users can understand work across agents, projects, and hubs.
Work
Project authorized NATS state into CopilotKit.
Show freshness and recover retained replay gaps.
Acceptance gate
Viewers converge after reconnect.
No cross-project leaks or duplicate execution.
P07-AC01 through P07-AC05
Owner: Frontend + interface platform
Notes: PROPOSED PHASE. Full authoritative phase definition follows. No acceptance criterion is claimed passed. Implementation remains paused pending Ryan's explicit authorization.
P07: AG-UI dashboard and Atomic Design
Status: proposed
Outcome: Authorized users can understand work across agents, projects, and hubs.
Accountable function: Frontend + interface platform
Relative size: L (complexity, not calendar duration)
Dependencies: P06
Work packages
1. Build a NATS-facing interface plugin that converts authorized state/events into a pinned AG-UI contract for CopilotKit.
2. Implement plans, tasks/boards, runs/attempts, agents/hubs, tool activity, agent conversations, evidence/artifacts, decisions/costs, settings, and domain contribution slots.
3. Use snapshots, ordered deltas, stable IDs/cursors, resynchronization, redaction, and explicit unknown/stale state.
4. Use atoms, molecules, organisms, templates, and feature/page composition. Implement keyboard, contrast, accessible names, empty/error/offline states.
5. Include approvals and run controls only to the approved scope. Commands always return to their authoritative owner over NATS.
6. Read authorized NATS-backed views with source revisions/checkpoint cursors. Show lag or rebuild status explicitly; destructive controls revalidate at the record owner instead of trusting cached display state.
Acceptance criteria
P07-AC01: Refresh, reconnect, duplicate events, delayed events, and history gaps converge to the same authorized view without starting work.
P07-AC02: An unauthorized user cannot access another project's snapshots, streams, conversation, or artifact by guessing an ID.
P07-AC03: Every displayed completion or cancellation state distinguishes worker output from accepted/confirmed state.
P07-AC04: Domain UI contributions use versioned registered components. Core views remain usable when an optional plugin fails.
P07-AC05: Reusable component boundaries and accessibility checks pass for all launch views.
Verification
1. Run multi-viewer browser tests, revoked-session tests, stream replay, and network interruptions.
2. Compare UI snapshots to authoritative records after each failure scenario.
3. Run component dependency checks, keyboard/screen-reader review, and visual regression tests.
Required evidence
- AG-UI event mapping
- UI extension and accessibility reports
- Dashboard before/after demonstration
Rollback / containment: Retain CLI access and pin the prior interface/UI version. A UI rollback cannot roll back task ownership.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 32
P08 Jev decision services
32
Plugins request bounded semantic advice with traceable evidence and safe fallback.
Work
Implement scoped definitions, cache, budgets and fallback.
Compare semantic quality and total workflow cost.
Acceptance gate
Jev cannot create authority.
Holdout and cost gates pass per definition.
P08-AC01 through P08-AC05
Owner: Decision platform + evaluation
Notes: PROPOSED PHASE. Full authoritative phase definition follows. No acceptance criterion is claimed passed. Implementation remains paused pending Ryan's explicit authorization.
P08: Jev decision services and measured efficiency
Status: proposed
Outcome: Plugins request bounded semantic advice with traceable evidence and safe fallback.
Accountable function: Decision platform + evaluation
Relative size: L (complexity, not calendar duration)
Dependencies: P07
Work packages
1. Implement a language-neutral decision service with optional Jev provider, versioned definitions/rubrics/schemas, scoped NATS requests, cache, budgets, cancellation, and evidence ledger.
2. Check exact rules and data-export authority before hosted inference. Distinguish known answer, abstention, partial evidence, unavailable provider, and ambiguous billing.
3. Support the eight reusable decision families and contributed definitions. Start in shadow/advisory mode for capability discovery, evidence selection, failure triage, and review.
4. Preserve exact source IDs/spans, required facts, contrary evidence, and context-expansion routes. Mandatory events bypass relevance filters.
5. Measure downstream tokens, provider costs, prompt-cache effects, latency, retries, rework, and accepted outcomes against a baseline.
Acceptance criteria
P08-AC01: Boot and core orchestration still work when Jev is disabled or unreachable, using documented fallbacks.
P08-AC02: Jev cannot grant authority, mutate kernel state, invent tool success, transfer task ownership, or accept a result.
P08-AC03: Cache keys bind tenant, scope, source/version, definition/model, and policy. Revoked sharing cannot return a cached restricted result.
P08-AC04: All calls obey size/time/budget limits and account for failed/uncertain attempts. Replay of stored annotations makes no new paid call.
P08-AC05: Each enabled definition passes its own labeled holdout criteria and workflow non-regression threshold before promotion.
Verification
1. Run the existing synthetic examples and 44-case policy illustration as historical inputs, then extend with real service and NATS tests.
2. Evaluate with provider mocks for mechanics, separately with capped live calls for semantic quality after local token configuration and budget approval.
3. Compare deterministic baseline, Jev tools only, and tools plus skills on equivalent fresh tasks.
Required evidence
- Decision contracts and policy ledger
- Definition-specific scorecards
- Cost per accepted outcome and fallback report
Rollback / containment: Disable a definition or provider and use the deterministic/manual fallback. Retain audit/evaluation history.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 33
P09 Portable Jev and first skills
33
The same Jev capabilities improve supported clients with host-specific packaging.
Work
Package tools and evaluate triggers and obligations.
Qualify local modes. Remote modes wait for P10.
Acceptance gate
Whole-suite near misses pass.
Actual-host, semantic and cost evidence support defaults.
P09-AC01 through P09-AC05
Owner: Skills + client integrations
Notes: PROPOSED PHASE. Full authoritative phase definition follows. No acceptance criterion is claimed passed. Implementation remains paused pending Ryan's explicit authorization.
P09: Portable Jev plugin and first skill wave
Status: proposed
Outcome: The same Jev capabilities improve supported clients with host-specific packaging.
Accountable function: Skills + client integrations
Relative size: L (complexity, not calendar duration)
Dependencies: P08
Work packages
1. Build one shared Jev CLI/MCP runtime and portable skill content with separate Claude, Codex, Pi, and Desktop packaging.
2. Keep standalone Jev usable without Agentmux or NATS. In Agentmux mode route decision requests through scoped hub services.
3. Create the proposed first general skill wave: setup, classify, scout, context, triage, review, author, and eval.
4. Create the first Agentmux wave: prepare-worker, delegate, inspect-hub, and review-results. Qualify local-hub behavior in P09 and keep remote-hub modes disabled until P10 actual-hub acceptance. Keep final delegation authorization with platform owners.
5. Use skill-creator to draft, run paired behavioral and trigger tests, review results, revise, and qualify untouched holdout cases.
Acceptance criteria
P09-AC01: All first-wave skills have a clear trigger, declared input/output, real use case, error/fallback behavior, and evaluation fixtures.
P09-AC02: Whole-suite near-miss tests show skills do not compete unnecessarily or trigger a broad ask-everything path.
P09-AC03: Every claimed host capability passes on that actual host. Unsupported hooks/compaction are declared.
P09-AC04: Skills preserve counterevidence and required obligations and cannot override system permissions or invent authority.
P09-AC05: Live semantic and end-to-end cost gates pass before the corresponding skill is enabled by default.
Verification
1. Run approximately 20 positive/near-miss trigger prompts per skill and representative task pairs plus shared boundary cases.
2. Use independent review and separate tuning/validation/release sets.
3. Measure skill discovery metadata overhead, context cost, accuracy, and accepted outcomes across hosts.
Required evidence
- Host packages and skill catalog
- Paired skill-creator evaluation reports
- Cross-host conformance and release holdout
Rollback / containment: Disable or uninstall the specific skill/package, preserve user config, and retain CLI/MCP access where independently qualified.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 34
P10 Connected hubs and leaf nodes
34
Independent teams share authorized work while retaining their own authority.
Work
Qualify independent domains and remote skills.
Test stale replicas, partitions and retention gaps.
Acceptance gate
Origin owns acceptance.
Lost acceptance replies and outages never cause blind redispatch.
P10-AC01 through P10-AC07
Owner: Federation + security + reliability
Notes: PROPOSED PHASE. Full authoritative phase definition follows. No acceptance criterion is claimed passed. Implementation remains paused pending Ryan's explicit authorization.
P10: Connected hubs, leaf nodes, and cross-organization work
Status: proposed
Outcome: Independent teams share authorized work while retaining their own authority.
Accountable function: Federation + security + reliability
Relative size: XL (complexity, not calendar duration)
Dependencies: P09
Work packages
1. Implement scoped trust agreements, node/peer enrollment, NATS leaf topology, independent JetStream domains where needed, and selective sharing/replication.
2. Publish authorized capabilities and capacity. Filter deterministic eligibility before optional Jev suitability scoring and revalidate at offer time.
3. Implement durable offer, acceptance, reservation, execution reporting, result submission, origin acceptance, reconciliation, revocation, and explicit reassignment.
4. Support work/context/artifacts/code/findings/messages/board projections with authenticated provenance, digests, visibility, and retention.
5. Add automatic receiving-hub acceptance inside approved rules, pending human approval for review-required work, and rejection for hard-denied work. Enforce any onward delegation/export separately.
6. Qualify and enable the remote-hub modes of P09 delegate, inspect-hub, and review-results skills on real connected hubs and supported clients. Their earlier local qualification does not count as federation evidence.
7. Use separate persistent JetStream domains for hubs that must operate autonomously. Share selected authorized records and views, preserve origin task versus receiver execution authority, and reconcile replication gaps without treating mirrors or merged sources as a shared mutable task.
Acceptance criteria
P10-AC01: Same-organization and cross-organization reference workflows both finish with origin-owned result acceptance.
P10-AC02: Accepted work stays reserved while disconnected. Missing acceptance acknowledgment remains ambiguous until reconciled, never automatically redispatched.
P10-AC03: Duplicate offer/result delivery creates one delegation/attempt outcome. Wrong executor, project, repository, or task version is rejected. Stale grants cannot authorize new effects. Authenticated historical results from previously authorized reserved work are retained for reconciliation or quarantine when current policy requires it; grant expiry cannot erase the obligation or its evidence.
P10-AC04: Unauthorized accounts cannot subscribe to private project subjects or fetch protected artifacts. Transitive hub connectivity grants no access.
P10-AC05: Reconnect recovers progress/results and durable revocations. A stop request is not reported as execution stopped until confirmed or clearly unknown.
P10-AC06: A leaf outage and independent local persistence produce the agreed offline behavior without treating broker connectivity as shared ownership.
P10-AC07: After a partition, mirror lag, retention gap or restoration of an older origin snapshot, hubs reconcile authoritative task and execution records before admitting overlapping work. Replication never grants write authority, and accepted or acceptance-unknown work remains reserved.
Verification
1. Run at least three hubs and two independently administered organizations with real accounts/leaf links and isolated stores.
2. Inject partitions before/after offer acceptance, drop replies, duplicate deliveries, restart hubs, expire/revoke grants, and alter task versions.
3. Exercise explicit cancel/reassign with a possibly running old worker and document unavoidable external-effect uncertainty.
4. Snapshot the origin before a remote acceptance, let the receiver accept and continue, restore that older origin snapshot, and require reconciliation before overlapping admission. Verify one reservation and no duplicate execution.
5. Disconnect beyond configured stream-retention and deduplication horizons using short test limits, then prune, restart, and reconnect. Require gap detection, snapshot/reconciliation or explicit intervention, preserved reservations, and no duplicate effects.
Required evidence
- Federation state-machine and authority tests
- Partition/reconciliation matrix
- Cross-organization demo with auditable evidence
- Independent-domain storage, retention-gap and older-origin recovery reports
Rollback / containment: Disable new links and stop new offers. Preserve reservations and reconcile accepted work before returning to a prior federation version.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 35
P11 Industrial packages
35
Industrial workflows extend Agentmux through the same contracts as other domains.
Work
Port domain and vendor behavior through plugin contracts.
Declare host/tool support and mutation safeguards.
Acceptance gate
Selected reference workflow passes.
Simulator claims stay separate from hardware qualification.
P11-AC01 through P11-AC05
Owner: Domain engineering + plugin SDK
Notes: PROPOSED PHASE. Full authoritative phase definition follows. No acceptance criterion is claimed passed. Implementation remains paused pending Ryan's explicit authorization.
P11: Industrial and vendor extension packages
Status: proposed
Outcome: Industrial workflows extend Agentmux through the same contracts as other domains.
Accountable function: Domain engineering + plugin SDK
Relative size: XL (complexity, not calendar duration)
Dependencies: P10
Work packages
1. Package industrial orchestration guidance, tools, schemas, UI renderers, and skills with explicitly independent or parent-owned children.
2. Migrate current Modbus, MQTT, network discovery, PROFINET snapshot/DCP, passive BOOTP, EtherNet/IP/Logix, ADS, EtherCAT diagnostics, CODESYS runtime tooling, PCAP analysis, and existing engineering wrappers to declared capability plugins.
3. Define CODESYS, Siemens, Rockwell, and related vendor integration slices with actual licensed tool/OS/hardware prerequisites and test environments.
4. Add engineering build/migration/evidence skills and Jev definitions for diagnostics and source-preserving comparisons.
5. Implement read/simulation-first reference workflows and per-action permissions for equipment changes. Resolve any Windows-native execution host arrangement explicitly.
6. Inventory existing PCM600/ABB-related privilege hooks as integration requirements, preserving target/action confirmation and audit. Do not infer a complete vendor adapter from the existence of a guard hook.
Acceptance criteria
P11-AC01: A selected industrial workflow completes through client, orchestration, tool plugin, evidence, and dashboard without kernel or generic task-model changes.
P11-AC02: Standalone and nested installation of selected domain children behave as declared.
P11-AC03: Every migrated existing integration has a parity/deprecation record, tested tool/platform matrix, and explicit missing capability status.
P11-AC04: Equipment writes require the correct target/action/operation grant and any applicable human approval at the owning tool endpoint.
P11-AC05: A vendor adapter passes with the actual required tool or a clearly labeled simulator. Simulated success is never sold as hardware qualification.
Verification
1. Use protocol simulators and recorded fixtures, then controlled hardware/vendor environments for supported claims.
2. Test wrong device/project/version, timeout, partial writes, lost replies, credential failure, and disconnected grants.
3. Demonstrate missing Windows-native prerequisites as an actionable unsupported environment, not silent fallback.
Required evidence
- Domain package and vendor compatibility matrix
- Industrial workflow and permission report
- Protocol parity and hardware qualification records
Rollback / containment: Disable the affected domain capability and drain sessions. Preserve device-state uncertainty and do not automatically reverse external equipment effects.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 36
P12 Production qualification
36
Customers can install, operate, recover, and support the complete launch product.
Work
Qualify install, upgrades and restore drills.
Prove history retention and rebuildable read models.
Acceptance gate
All launch evidence matches the candidate.
Ryan authorizes merge/release after review with Nick.
P12-AC01 through P12-AC06
Owner: Release + operations + product
Notes: PROPOSED PHASE. Full authoritative phase definition follows. No acceptance criterion is claimed passed. Implementation remains paused pending Ryan's explicit authorization.
P12: Production hardening and first sellable release
Status: proposed
Outcome: Customers can install, operate, recover, and support the complete launch product.
Accountable function: Release + operations + product
Relative size: XL (complexity, not calendar duration)
Dependencies: P11
Work packages
1. Finish signed/reproducible distributions, dependency locks/SBOM, versioned configuration, upgrade/rollback, package verification, and support diagnostics.
2. Complete self-hosted topology guides, backup/restore drills, durable retention/pruning, quotas/fairness, monitoring, alerts, incident procedures, and consented telemetry.
3. Validate launch performance/capacity profiles, broker/storage failure recovery, long-running work, and cross-organization safety.
4. Finish onboarding, documentation, reference plugins, accessibility, support ownership, commercial licensing/provider eligibility, and pilot feedback.
5. Rehearse migration from v0.32.0 across board/run/hub/federation state, credentials, worktrees, and integrations. Keep an explicit compatibility retirement plan.
6. Restore an origin hub while a receiver continues accepted work and reconcile outstanding reservations before admitting replacements. Test backup-name collisions, JetStream/checkpoint restore, and local filesystem requirements for any remaining SQLite indexes or legacy migration inputs.
7. Qualify NATS storage capacity, retention, immutable artifact lifecycle, snapshot/archive integrity, sync policy and recovery time for solo and team profiles. Document every remaining SQL component as a rebuildable projection or an explicitly reviewed exception.
Acceptance criteria
P12-AC01: Every launch requirement is linked to passing evidence for the exact release candidate. Critical correctness/security defects are closed.
P12-AC02: A new developer installs and completes the reference task using only published docs on every supported platform.
P12-AC03: A team administrator enrolls two organizations, shares a scoped project, delegates work, survives a partition, and restores a backup.
P12-AC04: The approved capacity/SLO targets and recovery drill pass without losing acknowledged durable records within the tested fault model.
P12-AC05: Ryan reviews the release evidence with Nick and explicitly authorizes merge/release. Passing automation alone cannot merge this branch.
P12-AC06: The approved NATS storage profile passes record/checkpoint/artifact restore, projection rebuild, retention-gap and migration rollback drills under the declared process/host/disk/quorum failure model. Published RPO/RTO and capacity claims match observed evidence, and no unreviewed SQL authority remains.
Verification
1. Run the complete release matrix, independent security review, load/soak tests, upgrade/restore rehearsal, and pilot acceptance.
2. Compare evidence manifests to the exact candidate digest and invalidate stale results after material changes.
3. Review support and commercial readiness with accountable owners.
4. Run qualified storage failure and recovery drills with pinned disk/sync/replication settings, including capacity exhaustion. Verify restored reservations before processing queued commands.
Required evidence
- Release readiness dossier
- Pilot and migration acceptance
- Signed merge/release decision
Rollback / containment: Use rehearsed backup/restore and version compatibility procedures. Stop new work where safe downgrade is impossible; reconcile in-flight tasks first.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 37
P13 Remaining Jev and skills
37
Every remaining research proposal receives a measured implementation decision.
Work
Evaluate remaining catalog ideas in bounded batches.
Qualify advanced context and supported compaction controls.
Acceptance gate
Every proposal retains a disposition.
Quality and full economics support each activation.
P13-AC01 through P13-AC04
Owner: Decision platform + domain owners
Notes: PROPOSED PHASE. Full authoritative phase definition follows. No acceptance criterion is claimed passed. Implementation remains paused pending Ryan's explicit authorization.
P13: Remaining Jev catalog and skill expansion
Status: proposed
Outcome: Every remaining research proposal receives a measured implementation decision.
Accountable function: Decision platform + domain owners
Relative size: L–XL per batch (complexity, not calendar duration)
Dependencies: P12
Work packages
1. Implement the complete remaining catalog in bounded batches using the coverage appendix, without duplicating overlapping video and original use cases.
2. Complete general extract, compare, checkpoint, integrate, and optimize skills plus remaining Agentmux planning, coordination, diagnosis, knowledge, plugin review, and policy-tuning skills.
3. Expand temporary bounded questions, semantic inventories, federated source inspection, compaction/retention controls, what-if replay, fidelity review, bilateral contract interpretation, and opportunity scorecards.
4. Promote only qualified definitions. Record rejected or deferred cases with evidence, reasons, owner, and next review point.
Acceptance criteria
P13-AC01: All 88 original uses, 14 video additions, four enablers, and 26 skills retain a traceable disposition and owning phase.
P13-AC02: Each batch passes schema, access, failure, semantic holdout, host-capability, and end-to-end economic gates.
P13-AC03: Compaction preserves mandatory obligations and active evidence and runs only on supported hosts.
P13-AC04: No savings claim relies only on shortened context or a provider's confidence score. Outcome quality and total cost meet approved thresholds.
Verification
1. Repeat the P08/P09 evaluation protocol per changed definition/skill and representative combined workflows.
2. Use stored factors for policy-only replay and record when a fresh inference is necessary.
3. Run regression tests for cache isolation, missing evidence, mandatory messages, provider failure, and decision drift.
Required evidence
- Catalog disposition register
- Per-batch holdout and economics
- Complete skill-suite release matrix
Rollback / containment: Independently disable definitions/skills and return to the prior pinned set while preserving all evidence.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 38
P14 Sandboxed plugins
38
Untrusted third-party plugins gain a tested containment option.
Work
Define and enforce per-platform containment profiles.
Retain compatible contracts and explicit trusted exceptions.
Acceptance gate
Adversarial escape tests pass.
Only qualified profiles claim untrusted-plugin support.
P14-AC01 through P14-AC04
Owner: Security + plugin platform
Notes: PROPOSED PHASE. Full authoritative phase definition follows. No acceptance criterion is claimed passed. Implementation remains paused pending Ryan's explicit authorization.
P14: Sandboxed plugins and ecosystem expansion
Status: proposed
Outcome: Untrusted third-party plugins gain a tested containment option.
Accountable function: Security + plugin platform
Relative size: XL (complexity, not calendar duration)
Dependencies: P13
Work packages
1. Choose and threat-model isolated execution profiles, process/container/WASM options, host brokers, and platform limitations against actual plugin needs.
2. Enforce declared filesystem/network/process/device access, secret isolation, quotas, termination, and package provenance at runtime.
3. Qualify UI contribution isolation and publisher/distribution controls before enabling a public plugin ecosystem.
4. Retain trusted native profiles only with clear administrator choice. Assess future hosted service and native Windows as separate product decisions.
Acceptance criteria
P14-AC01: Adversarial plugins fail to escape their declared profile or access unauthorized host/team data in the supported threat model.
P14-AC02: Sandboxed and trusted implementations pass the same language-neutral domain contract tests.
P14-AC03: Required native/device integrations declare and enforce narrower support or an explicitly trusted execution host.
P14-AC04: Security review and per-platform tests pass before claiming untrusted-plugin support. Marketplace availability requires this gate or a clearly restricted trusted catalog.
Verification
1. Run exploit-oriented confinement, resource exhaustion, cross-tenant, lifecycle, dependency, and upgrade tests on each supported profile.
2. Review residual risk and performance/compatibility effects with independent security expertise.
3. Re-run representative local, team, federation, UI, and industrial workflows.
Required evidence
- Sandbox threat model and test report
- Profile compatibility matrix
- Ecosystem launch decision
Rollback / containment: Disable new untrusted profiles/packages and preserve the prior trusted-only support promise.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 39
Proposed capacity and responsiveness
39
Profile | Proposed workload | Purpose
Solo | 1 user, 2 projects, 4 attempts | Local overhead
Team | 20 users, 10 projects, 40 attempts | Isolation and contention
Federation | 3 hubs, 2 organizations | Partition recovery
Growth benchmark | 200 users, 10 hubs, 400 attempts | Find later bottlenecks
Starting targets for review
Metadata p95 <250 ms Dashboard update ≤2 s 10,000-event replay ≤5 s
Notes: All numbers are reviewable proposed test profiles, not measured capacity or service commitments. Plan section 8: solo 1 user/2 projects/4 attempts; team 20 users/10 projects/40 attempts; federation 3 hubs/2 organizations/up to 40 attempts per hub; growth 200 users/10 hubs/up to 400 overall. Proposed p95 metadata <250ms, UI <=2s after owner record, 10,000-event replay <=5s, warm-broker readiness <=10s, prepared setup <=15min after tools/accounts. Approve hardware, payloads, latency, retention and variance before measurement. RPO/RTO remain explicit choices.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 40
Verification across real failure boundaries
40
Mechanics
Schema, identity, replay, transaction boundaries and idempotency
Actual environments
Pinned client versions, macOS/Linux/WSL, real NATS and browser recovery
Semantic outcomes
Untouched task cases, independent labels, complete cost and rework
Operations
Partition, revocation, disk pressure, backup restore and migration rollback
Notes: Future verification obligations. The final plan contains 15 phases and 75 acceptance criteria. The companion verification matrix contains 48 failure scenarios. Require contract tests, actual broker and SDK qualification, client-host workflows, negative authority tests, fault injection, UI replay/accessibility and restore drills. Specific persistence tests include one-stream atomic commit, unknown acknowledgements, stale view denial, history retention, projection rebuild, independent offline domains, replica freshness, and object digest/backup recovery. Historical baseline suites do not establish future product acceptance. Six known baseline findings remain open until P01 repairs/disproof and regressions pass.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/verification-matrix.json
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/known-baseline-blockers.md

## Slide 41
Open decisions and delivery risks
41
Decision | Review needed before
Proof workflow and dashboard commands | P00 exit
Runtime, SDKs, NATS profiles and account layout | P01–P04 implementation
Client/vendor versions and commercial terms | Supported integration claims
Capacity, recovery, staffing and dates | Release promises
Jev data policy, budgets and thresholds | Capped live evaluation
Risks concentrate in bootstrap, distributed authority, client coverage and active-work migration.
Notes: NATS-first shared persistence with optional rebuildable SQL views is approved. Open implementation choices include runtime and SDK versions, stream/bucket/account boundaries, replica counts, storage durability and capacity, retention/snapshot recovery contracts, actual client versions, commercial terms, dashboard command scope and cost policies. None of these unresolved details reopens the approved minimal-kernel, scoped-owner or disconnected-work authority boundaries.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 42
Review and authorization
42
Resolve P00 choices
Approve or revise the phase sequence and proposed targets
Name gate reviewers and record the accepted plan revision
Implementation starts only after Ryan’s explicit authorization
Planning is ready for review. Repository governance remains blocked
until approved P01 correctness repairs pass.
Notes: Proposed next action: Ryan and Nick review the plan and criteria, resolve P00 choices, approve/revise first-release split and targets, name reviewers and record approved revision. Ryan explicitly authorizes implementation. Later merge/release is a separate decision after review. This deck and current work do not authorize product implementation. Planning is ready for review, while the repository governance gate remains blocked by inherited correctness findings until approved P01 repairs and regressions close them. Presentation package validation is separate from repository governance and product acceptance.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json
C:/Users/RyanHelms/GitHub/agentmux/.bytedesk/design-patterns/review.json