## Slide 1
Agentmux
Platform implementation review
Architecture, migration and phased acceptance
Proposal for Ryan and Nick
October 9, 2026
Notes: Planning and presentation only. No future product functionality or acceptance test is claimed complete. Baseline df46e94570fadf78ef67a75a692dd48b968a10f7, Agentmux 0.32.0. All rearchitecture work belongs on feat/agentmux-platform-rearchitecture. Ryan reviews with Nick and explicitly authorizes merge.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md

## Slide 2
Confirmed product direction
02
Plugin foundation
A protected boot assembly with extensible surrounding services
NATS communication
All Agentmux components communicate through scoped NATS contracts
Client-led work
Existing agent clients lead the workflow; the dashboard shows shared activity
Local and connected teams
Native macOS/Linux, Windows through WSL, self-hosted hubs across organizations
Notes: Accepted decisions are distinct from proposed implementation details. Native Windows runtime, hosted service, runtime language, SDK languages and dashboard command scope have not been committed.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/agentmux-product-architecture-working-brief.md

## Slide 3
Current architecture
03
Agent clients
and terminal
Bash / tmux
harness
Provider processes
and worktrees
Python hub
Federation
extensions
NATS
shared circle
Local dashboard
Board SQLite
Run files and claims
Hub SQLite
Separate ownership and completion signals need explicit migration.
Notes: Verified baseline. Multiple local stores and transport paths coexist. NATS federation is present, but local component communication is not universally NATS. Current federation uses direct broker clients and in-process Python extensions.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/implementation-baseline-review.md
C:/Users/RyanHelms/GitHub/agentmux/agentmux.sh
C:/Users/RyanHelms/GitHub/agentmux/hub/server.py
C:/Users/RyanHelms/GitHub/agentmux/hub/fed/runtime.py

## Slide 4
Proposed product architecture
04
Agent clients
Client integrations
CopilotKit dashboard
NATS application backbone
AG-UI interface
Plans / tasks
and workspaces
Execution / tools
and domain plugins
Identity / policy
and owned storage
Connected
team hubs
Protected kernel publishes permitted status into a separate application scope.
Notes: Target component responsibilities. Every ordinary product capability uses plugin contracts. The operating system and broker are bootstrap infrastructure. External native tool I/O stays inside the owning plugin. UI transport terminates at the interface plugin.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/agentmux-product-architecture-working-brief.md
https://docs.nats.io/
https://docs.ag-ui.com/introduction

## Slide 5
Protected kernel boundary
05
Protected boot assembly
Boot and protected-plugin lifecycle
Internal NATS communication
Published kernel status
Surrounding subscribers
Identity, storage, orchestration and domain services live outside this boundary.
Kernel replacement and general external kernel commands remain excluded.
Notes: Accepted minimal kernel: boot, lifecycle of protected plugins, internal communication and status publication. Outside plugins have only permitted subscriptions to published kernel information. No general inbound kernel write interface is approved. Surrounding supervisor owns ordinary plugin lifecycle. Deterministic boot does not depend on an LLM, Jev or identity-provider availability.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/agentmux-product-architecture-working-brief.md

## Slide 6
Nested plugins and scoped context
06
Parent plugin
Parent-owned child
Independent child
PluginContext
Identity, logger, config,
lifecycle and scoped clients
OperationContext
Caller, project, grant,
attempt and deadline
Independent reuse survives parent removal. Concurrent callers never share a mutable “current user.”
Notes: Package relationship, runtime instance ownership and placement are separate declarations. PluginContext carries stable package/instance identity and scoped services. OperationContext carries validated caller/project/task/attempt/grant and deadline. Children inherit allowed defaults, not unlimited authority or a raw service container. Initial trusted native plugins are not hostile-code confinement.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 7
NATS service responsibilities
07
Facility | Planned responsibility | Required distinction
Core request/reply | Queries and live status | Timeout may mean unknown
JetStream | Durable work, results and replay | Delivery differs from acceptance
KV and Object Store | Registry, configuration and artifacts | Revisions, digests and access
Accounts | Kernel, tenant and partner boundaries | Actual broker enforcement
Leaf topology | Connected sites and execution hosts | Explicit storage and replication
A database may sit inside its owning plugin. Other plugins reach it through NATS.
Notes: Proposed service allocation, subject to pinned-version tests. Core timeout may leave an unknown outcome. JetStream requires declared ack points, redelivery handling and persistence/fault assumptions. KV TTL does not revoke task ownership. Leaf links do not automatically provide offline storage or stream replication.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
https://docs.nats.io/
https://docs.nats.io/learn/topologies/leafnodes

## Slide 8
Developer workflow before and after
08
Today
Launch a pane
Send prompts
and inspect output
Update several
work records
Review files
and approvals
Proposed
Request work
in a client
Track plan
and scoped attempts
Inspect evidence
and conversations
Accept result
at the origin
Client and dashboard connections may close while durable work continues.
Notes: Before workflow is a summary of existing separate harness/task/run steps. After is the proposed complete reference workflow. Existing external client sessions and Agentmux-owned workers are different resources. Publishing and merging require explicit authority.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/implementation-baseline-review.md

## Slide 9
Concurrent users and workspaces
09
Developer A
Developer B
Project A scope
Project B scope
Owned attempts
and worktrees
Owned attempts
and worktrees
Validated caller and grant on every operation
P04 also qualifies worker OS/container/host separation for mutually untrusted task code.
Notes: Proposed identity/workspace model. Isolation must apply to reads, subscriptions, artifact access, secret resolution and commands. Worktree isolation separates Git state but does not by itself provide process security. Shared work requires explicit coordination and ownership.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 10
Federated ownership
10
Origin hub
Task and acceptance owner
Receiving hub
Delegated execution owner
Scoped NATS link
Local execution host
with declared offline grants
Offer and grant
Progress and evidence
Origin acceptance
A result submission preserves executor, task version, artifact digest and provenance.
Notes: Origin owns task and final result acceptance. Receiver owns delegated execution. The proposed launch includes independently administered organizations. A scoped NATS link permits only explicitly exported services/data. Transitive connectivity provides no implicit access. Local and team persistence/failure behavior must be tested.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json
https://docs.nats.io/learn/topologies/leafnodes

## Slide 11
Disconnected work stays reserved
11
Offer
Accepted
and reserved
Execution
Acceptance unknown
Reply lost
Disconnected
Reservation retained
Result submitted
Origin reviews
A connectivity timeout never authorizes reassignment.
Receiver may continue within its grant and reconcile the same delegation after reconnect.
Expired grants block new effects. Historical results remain available.
Notes: No automatic timeout edge from accepted or acceptance-unknown delegation to execution on another hub. Lost acceptance reply can hide a successful acceptance. Receiver may continue within its offline grant. Reassignment is explicit, records prior attempt and cannot guarantee reversal of external effects. Revocation cannot instantly stop an isolated machine.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 12
Authorization at the work owner
12
Validated caller
Broker subject
permissions
Authoritative owner
checks and transition
Revalidation
Current grants, task version, approval and artifact identity
Policy outcomes
Allow, hard deny or review required. Approval cannot override a hard denial.
Launch isolates worker code. P14 separately qualifies untrusted third-party plugins.
Notes: Proposed two-layer enforcement. Broker permissions limit message/API reach. Authoritative service validates actor, operation scope, policy, task version, approval and state. NATS possession or an agent claim alone cannot grant domain authority. Trusted plugins initially can still abuse OS privileges, so scope claims must match that trust assumption.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 13
AG-UI dashboard projection
13
NATS records
and events
Authorized
interface plugin
AG-UI
CopilotKit dashboard
Plans and tasks
Work, agents and evidence
Agent conversations
Snapshots and ordered updates
Reconnect and missing-history recovery
Atoms, molecules, organisms, templates
Dashboard actions remain a P00 scope decision. Any enabled command returns to its owner.
Notes: Accepted UI direction and proposed mapping. NATS retains internal communication and authoritative ownership. AG-UI is the UI-facing event contract. CopilotKit supplies interface facilities. Snapshot/revision/replay authorization must be implemented by the platform. Display only supported client events, authored plans/messages and emitted summaries; no claim of private model reasoning access.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
https://docs.ag-ui.com/concepts/events
https://docs.ag-ui.com/concepts/state
https://docs.copilotkit.ai/
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/agentmux-product-architecture-working-brief.md

## Slide 14
Optional Jev decision pipeline
14
Exact eligibility
and export policy
Bounded evidence
and versioned question
Optional Jev
decision
Deterministic policy
and revalidation
Authorized owner
executes or abstains
Decision and
outcome evidence
Jev advice cannot grant permissions, release reservations or accept a result.
Notes: Proposed optional semantic service. Exact eligibility and data export checks occur before hosted inference. Jev supports bounded decisions; it is not used to generate arbitrary summaries or code. Policies revalidate current state and grants before any command. Abstention, unavailable provider, invalid output, stale source and uncertain billing remain explicit. Boot and ordinary orchestration work without Jev.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/agentmux-jev-integration-report.md
https://docs.typesafe.ai/introduction

## Slide 15
Measuring token and cost savings
15
Comparison | Measure on equivalent tasks
Existing workflow | Accepted outcomes, engineer time, tokens and total cost
Jev tools | Add Jev cost, retries, failed calls and cache changes
Jev tools plus skills | Add trigger accuracy, evidence retention and rework
Proposed activation threshold
At least 10% lower total cost per accepted outcome, with approved quality limits
Fewer downstream tokens can still cost more when prompt caching deteriorates.
Notes: No measured Agentmux product savings are claimed. Earlier offline scenario math uses illustrative LLM prices/volumes and shows a cache-loss counterexample. P08 proposes independent comparisons of baseline, Jev tools and tools+skills, with final untouched cases. Proposed default-activation target is >=10% lower total cost per accepted outcome and <=2 percentage-point accepted-outcome degradation, with uncertainty reported. These values need approval and adequate sample sizes. Classifier thresholds are definition/risk-specific. Pilot productivity comparisons use matched baseline tasks and report time to first accepted change, engineer active minutes, elapsed time, review iterations, reopened work, escaped defects, recovery effort and cost per accepted outcome, with sample size and task mix.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/jev-efficiency-scenarios.mjs
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 16
Portable Jev and Agentmux skills
16
Portable jev plugin: 13 proposed skills
Bounded classification, source inspection, evidence checks and context selection
Agentmux integrations: 10 proposed skills
Task and delegation advice using scoped hub contracts
Industrial packages: 3 proposed skills
Engineering evidence and diagnostics within declared domain permissions
Shared runtime, distinct skill triggers, host-specific packaging and actual-host evaluation.
Notes: The skill-suite proposal contains 13 general, 10 Agentmux-specific and 3 industrial skill proposals, totaling 26. Names, triggers and defaults remain for discussion and evaluation. They are not 26 installed skills. General skills are useful independently of Agentmux; Agentmux skills bind to authorized hub contracts; domain skills ship in industrial packages. CLI/MCP runtime portability does not imply identical hooks, compaction or event capture on each host.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/jev-plugin-skill-suite-proposal.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 17
Industrial extension packages
17
General orchestration contracts
Industrial engineering package
Guidance, workflows and evidence rules
Vendor and tool children
CODESYS / Siemens / Rockwell
Declared execution host and tool versions
Read, validate and mutate operations have separate permissions and evidence
Notes: Industrial controls is an optional domain layer, not a specialization of the general kernel. Preserve current operational modules and explicitly select supported vendor/tool/host versions. CODESYS, Siemens and Rockwell are vendor families to scope, not claims of complete current automation. Simulated transport tests do not qualify device writes. Unknown external outcome prevents blind retries.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/implementation-baseline-review.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 18
Migration with one authoritative writer
18
Inventory
and snapshot
Import and
reconcile
Compare
read-only views
Switch new
operations
Preserved evidence
Task IDs, run history, approvals and artifacts
Pending delivery and delegation state
Dirty worktrees and unmerged branches
Legacy retirement follows parity, migration rehearsal and an explicit recovery decision.
Notes: Proposed cutover: inventory source state and semantics, versioned export/import, read-only comparisons, writer cutover, recovery proof then explicit retirement. Preserve stable IDs and evidence, pending messages, dirty worktrees and unmerged branches. Never replay historical completed commands or assume external side effects reverse with local rollback.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/implementation-baseline-review.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 19
Phase acceptance and evidence
19
Implement
Verify criteria
Independent
review
Authorize
advancement
Evidence belongs to an exact revision
Source, contracts, environments, commands, results and rollback rehearsal
Unverified stays visible
A skipped environment or agent “done” message does not pass a gate
Merge and release require the separate Ryan/Nick review and Ryan’s explicit authorization.
Notes: Proposed gate record includes phase/revision, commit, dependency/config/schema versions, criterion IDs, environment/dataset, commands/exit codes, artifacts, fault tests, limitations, rollback rehearsal, independent reviewer and authorized advancement. Each phase depends on accepted predecessor. Skips and mock-only substitutes are gaps. Material changes invalidate affected evidence. Waivers cannot change accepted authority/security/kernel/reservation/merge invariants.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 20
Proposed delivery sequence
20
Phases | Primary outcome
P00–P04 | Decisions, contracts, boot, plugins and scoped ownership
P05–P07 | Local workflow, supported clients and dashboard
P08–P09 | Evaluated Jev services and portable skills
P10–P12 | Connected hubs, industrial packages and release evidence
P13–P14 | Remaining experiments and sandbox qualification
Launch recommendation: P00–P12. No dates or staffing commitments are implied.
Notes: P00-P12 is the proposed first-release sequence, including initial-release cross-organization federation. P13 preserves remaining evaluated Jev/skill proposals, and P14 qualifies sandboxing later. This release split is proposed, not an approved scope reduction. All phases promote sequentially. Independent preparation may overlap only within approved contracts. Relative sizes are not dates.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 21
P00 Scope and baseline
21
An approved implementation contract with no unresolved decision hidden in code.
Work
Resolve workflow, stack, storage and support decisions.
Inventory behavior and reproduce critical defects.
Acceptance gate
Reviewed plan and traceability.
Ryan authorizes implementation.
P00-AC01 through P00-AC04
Owner: Product + architecture
Notes: PROPOSED PHASE. Full authoritative phase definition follows, including all acceptance criteria, verification, evidence and rollback. No criteria are claimed passed.
P00: Scope, baseline, and architecture decisions
Status: proposed
Outcome: An approved implementation contract with no unresolved decision hidden in code.
Accountable function: Product + architecture
Relative size: M (complexity, not calendar duration)
Dependencies: none
Work packages
1. Freeze df46e94570fadf78ef67a75a692dd48b968a10f7 as the behavioral comparison baseline and inventory every CLI verb, dashboard view, protocol, state store, integration, and evaluation.
2. Resolve launch workflow, dashboard controls, language/runtime and initial SDKs, storage topology, NATS account/domain layout, supported OS/tool versions, initial scale, identity enrollment, and provider/data policy.
3. Reproduce or explicitly scope the previously reported federation correctness defects. Turn each into a regression case owned by the replacing phase.
4. Approve versioned state machines, authority boundaries, plugin manifest/context schemas, migration ownership, and the requirement-to-phase matrix.
Acceptance criteria
P00-AC01: Every accepted user decision and all existing functional groups have a named owner phase and verification scenario.
P00-AC02: Ryan and Nick review the plan and decision log. Ryan explicitly authorizes implementation before P01 starts.
P00-AC03: All P01–P04 blocking choices have recorded alternatives, rationale, and consequences. Later choices have a deadline before their owning phase.
P00-AC04: Baseline checks identify passes, failures, missing environments, and historic-only claims separately.
Verification
1. Review the traceability matrix and inspect contracts together.
2. Run existing relevant suites on supported environments and reproduce the four reported crash/dispatch defects with isolated fixtures.
3. Record the exact commit, tools, fixtures, and results. Review missing environments as gaps, not passes.
Required evidence
- Approved plan revision and decision log
- Baseline behavior inventory and defect fixtures
- Compatibility and capacity profiles
Rollback / containment: Planning only. Preserve current checkout behavior and the existing review history.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 22
P01 Contracts and verification
22
Contracts and failure scenarios can be tested before business plugins grow.
Work
Version contracts and repair inherited correctness blockers.
Build fault fixtures and spike two-hub reservations.
Acceptance gate
Independent clients interoperate.
Required regressions and governance checks pass.
P01-AC01 through P01-AC04
Owner: Architecture + quality
Notes: PROPOSED PHASE. Full authoritative phase definition follows, including all acceptance criteria, verification, evidence and rollback. No criteria are claimed passed.
P01: Executable contracts, baseline repairs, and verification
Status: proposed
Outcome: Contracts and failure scenarios can be tested before business plugins grow.
Accountable function: Architecture + quality
Relative size: L (complexity, not calendar duration)
Dependencies: P00
Work packages
1. Publish language-neutral command/event schemas and compatibility rules with organization, project, task, delegation, attempt, operation, schema version, and trace identifiers.
2. Create reusable contract fixtures and controllable fake workers/providers plus real NATS integration environments for CI.
3. Specify lifecycle, delivery acknowledgment, idempotency, deadline, cancellation, approval, and unavailable/unknown result semantics.
4. Establish per-phase evidence records, dependency gates, migration fixtures, and security/quality regression jobs.
5. Build an early two-hub contract spike with separate broker accounts and a leaf link. Exercise lost acceptance acknowledgment and reservation reconciliation before the later production federation phase.
6. Repair the six known baseline blockers after implementation approval, with focused regressions and truthful governance evidence. This prevents existing violations from blocking every later phase while waiting for the new federation layer.
Acceptance criteria
P01-AC01: Two independently implemented test clients exchange valid requests and reject incompatible or malformed envelopes.
P01-AC02: Fixtures cover duplicate, delayed, out-of-order, unauthorized, canceled, timed-out, and replayed messages without conflating execution with delivery.
P01-AC03: A failing predecessor gate prevents promotion. Waivers cannot bypass accepted ownership or security invariants.
P01-AC04: CI captures exact versions and logs without recording credentials or private model reasoning. Known baseline blockers are repaired or disproved with evidence, and the required repository governance gate passes before P02 progression.
Verification
1. Run schema/contract suites in macOS, Linux, and WSL test jobs.
2. Break one contract fixture and one phase gate deliberately and confirm the pipeline refuses promotion.
3. Exercise a real broker restart and reconnect in the harness.
Required evidence
- Contract version 1 fixtures
- Failure injection harness
- CI gate and compatibility reports
Rollback / containment: Keep the new test path isolated from the legacy runtime. If a baseline repair is reverted, reopen its finding and invalidate the affected regression and phase-gate evidence.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 23
P02 Protected boot and NATS
23
A local installation boots deterministically with protected kernel plugins.
Work
Bootstrap broker access and protected plugins.
Publish status with bounded recovery and diagnostics.
Acceptance gate
Boot without hosted inference.
Outside plugins cannot write into the kernel.
P02-AC01 through P02-AC04
Owner: Runtime + messaging
Notes: PROPOSED PHASE. Full authoritative phase definition follows, including all acceptance criteria, verification, evidence and rollback. No criteria are claimed passed.
P02: Protected boot and the NATS foundation
Status: proposed
Outcome: A local installation boots deterministically with protected kernel plugins.
Accountable function: Runtime + messaging
Relative size: L (complexity, not calendar duration)
Dependencies: P01
Work packages
1. Implement a minimal launcher that establishes the configured NATS substrate and loads the fixed protected boot assembly.
2. Implement boot, protected-plugin lifecycle, protected internal communication, and deliberate publication of kernel status.
3. Separate protected internal subjects/accounts from exported information and surrounding application services.
4. Provide readiness snapshots, bounded startup/shutdown, broker recovery, basic installer/doctor skeleton, and local bootstrap diagnostics.
Acceptance criteria
P02-AC01: macOS, Linux, and WSL installations boot without an LLM or hosted Jev connection.
P02-AC02: An outside plugin can subscribe only to permitted kernel information and cannot publish commands or writes into the kernel.
P02-AC03: Bad configuration, occupied ports, unavailable broker, and failed protected plugin produce actionable bounded failures.
P02-AC04: Surrounding plugin failure does not corrupt boot state. Ordinary runtime communication uses NATS after bootstrap.
Verification
1. Capture broker traffic and audit permissions while running normal and unauthorized clients.
2. Cold-start and restart each platform. Kill NATS and one protected plugin at controlled points.
3. Verify late subscribers receive a consistent readiness snapshot and updates.
Required evidence
- Boot and shutdown matrix
- Kernel publication contract and permission tests
- Bootstrap recovery guide
Rollback / containment: Disable the new runtime entrypoint and retain the old launcher. No legacy data conversion yet.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 24
P03 Plugin framework and context
24
A third-party author can build a compatible trusted plugin without changing the kernel.
Work
Implement package lifecycle and both child modes.
Supply scoped contexts and interoperable SDKs.
Acceptance gate
Children cannot widen authority.
Two languages pass shared contracts.
P03-AC01 through P03-AC05
Owner: Plugin platform + SDK
Notes: PROPOSED PHASE. Full authoritative phase definition follows, including all acceptance criteria, verification, evidence and rollback. No criteria are claimed passed.
P03: Plugin framework, nested packages, and inherited context
Status: proposed
Outcome: A third-party author can build a compatible trusted plugin without changing the kernel.
Accountable function: Plugin platform + SDK
Relative size: XL (complexity, not calendar duration)
Dependencies: P02
Work packages
1. Implement manifest validation, dependency/version resolution, lifecycle supervision, package provenance, configuration schemas, and contribution registration.
2. Support independently reusable and parent-owned child packages, separately declaring runtime instance ownership and placement.
3. Inject PluginContext and per-call OperationContext. Supply identity, scoped logger, tracing/metrics, config, lifecycle, clock, and approved NATS service clients.
4. Add declared storage, artifacts, secrets, workspace, process, policy, and decision handles without sharing raw service implementations or an unrestricted container.
5. Build starter SDKs and conformance tooling in at least two selected languages. Provide install/upgrade/disable/uninstall and drain behavior.
Acceptance criteria
P03-AC01: Both child package modes install and activate correctly. Removing one parent retains independent children used elsewhere.
P03-AC02: Two concurrent users cannot overwrite an ambient current-user/current-project value. A child cannot widen its grant or forge logger identity.
P03-AC03: Dependency cycles, missing versions, partial initialization, and stale handles fail deterministically and clean up resources.
P03-AC04: A plugin in each selected language passes the same contract fixtures and interacts with another plugin over NATS.
P03-AC05: The protected kernel has no replacement option in package management. Trusted native code is accurately documented as unsandboxed.
Verification
1. Run an independent author exercise using only published SDK/docs.
2. Test lifecycle/resource leaks, dependency failure, configuration precedence, version skew, and upgrades with active operations.
3. Inspect NATS traces and execute negative tests at remote resource owners.
Required evidence
- Plugin manifest and SDK reference
- Conformance matrix and author tutorial
- Nested-package/lifecycle test report
Rollback / containment: Pin the last working package set, drain active work, and restore compatible configuration. Never silently downgrade incompatible storage.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 25
P04 Identity, state and workspaces
25
Multiple users and projects share a hub with explicit authority and durable ownership.
Work
Enroll identities and persist scoped ownership.
Qualify worker OS/container/host isolation and recovery.
Acceptance gate
Cross-scope access fails.
Crashes, duplicate requests and restores preserve ownership.
P04-AC01 through P04-AC05
Owner: Security + data platform
Notes: PROPOSED PHASE. Full authoritative phase definition follows, including all acceptance criteria, verification, evidence and rollback. No criteria are claimed passed.
P04: Identity, projects, durable state, and workspaces
Status: proposed
Outcome: Multiple users and projects share a hub with explicit authority and durable ownership.
Accountable function: Security + data platform
Relative size: XL (complexity, not calendar duration)
Dependencies: P03
Work packages
1. Implement human, device, service, and plugin identities, enrollment/revocation, organization/project membership, permissions, approvals, and audit outside the kernel. Distinguish allowed, denied, and review-required actions; ordinary approval cannot override a hard denial.
2. Implement authoritative storage owners, transactional state plus durable publication, deduplication, artifact digests, retention, backup/restore, and migrations.
3. Provide scoped workspace/Git/worktree management, configuration, connection/secret references, quotas, and resource reservations.
4. Provide local single-user defaults and self-hosted identity configuration using the same contracts.
5. Implement the approved worker execution profile so mutually untrusted task code cannot share unrestricted access to another user's files or credentials. Qualify OS/container/host separation independently of the later third-party-plugin sandbox.
Acceptance criteria
P04-AC01: Cross-user/project/organization negative tests deny unauthorized commands, subscriptions, files, artifacts, and secret resolution.
P04-AC02: State changes and their durable outgoing events survive crashes at every defined transaction boundary.
P04-AC03: Duplicate delivery returns the existing outcome and does not allocate a second workspace or task.
P04-AC04: Backup/restore preserves ownership and result provenance. Migrations preserve dirty worktrees and unmerged branches.
P04-AC05: Node revocation and secret rotation have tested online behavior and explicit offline limits.
Verification
1. Run the permission matrix against application owners and real broker accounts. Run an adversarial worker that attempts cross-project file, process, network, and credential access under the supported execution profile.
2. Inject failures before/after commit and publish acknowledgment, exhaust disk/quota, and restore from backup.
3. Run concurrency tests against every supported storage provider. Reject a provider that lacks required guarantees.
Required evidence
- Threat model and permission matrix
- Storage capability and migration contracts
- Recovery and isolation reports
Rollback / containment: Quiesce writers, take backups, switch owners only at a verified boundary, and restore the old owner if no new-schema writes have occurred.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 26
P05 Local orchestration
26
A developer can finish a reviewable software task through durable coordinated work.
Work
Implement plans, assignments and supervised attempts.
Deliver software changes with reviewable evidence.
Acceptance gate
Complete reference workflow.
Acceptance requires owner review, not terminal text.
P05-AC01 through P05-AC05
Owner: Orchestration + developer workflow
Notes: PROPOSED PHASE. Full authoritative phase definition follows, including all acceptance criteria, verification, evidence and rollback. No criteria are claimed passed.
P05: Local orchestration and evidence-based completion
Status: proposed
Outcome: A developer can finish a reviewable software task through durable coordinated work.
Accountable function: Orchestration + developer workflow
Relative size: XL (complexity, not calendar duration)
Dependencies: P04
Work packages
1. Implement project plans, tasks, dependencies, boards, role/agent/team definitions, assignment, run/attempt state, claims, resource scheduling, and explicit acceptance.
2. Implement supervised workers, session resume capability, isolated worktrees, tool calls, messages, handoffs, progress, conversation records, artifacts, validation, and review workflows.
3. Separate provider/process exit, reported completion, verified evidence, and owner acceptance. Model cancellation-requested, canceled, failed, and unknown states.
4. Port existing journal/notice/dead-letter, search/knowledge, code sharing, cost/resource, and orchestration evaluation behavior behind plugins.
5. Produce a software-change workflow from request through test evidence and a reviewable diff/PR proposal. Publishing and merging follow explicit permissions.
6. Preserve epics, sprints, ADR/capability proposal records, WIP/readiness gates, notifications, objections, and independent reviewer policy. Bind reviews to immutable repository/commit/artifact identities across multiple repositories.
Acceptance criteria
P05-AC01: A complete fixture workflow creates a plan, delegates tasks, executes in isolated workspaces, validates the result, and returns reviewable evidence.
P05-AC02: Two developers working on different or shared projects do not steal each other's claims, sessions, workspaces, or tool credentials.
P05-AC03: No task becomes accepted from terminal text, process exit, or a worker's self-reported done event alone.
P05-AC04: A crashed or disconnected worker leaves a recoverable known or explicitly unknown attempt. Retry preserves the prior attempt and its effects.
P05-AC05: Every P05-owned legacy functional group has parity evidence or an explicit replacement and data migration decision. Later client, dashboard, federation, and domain groups have an owned inventory and migration plan, with parity gated in their own phases. Changed artifacts invalidate bound approvals, and migration preserves distinct board, run, hub-work, and shared-board identities.
Verification
1. Run normal, failure, retry, cancellation, resume, parallel-team, cross-repo, and swarm-style scenario suites.
2. Inject crash windows around work attribution and result publication identified in the repository analysis.
3. Use real CLI worker smoke tests plus deterministic fake workers for exhaustive state transitions.
Required evidence
- End-to-end workflow recording
- Completion/ownership invariant report
- Legacy parity and migration checklist
Rollback / containment: Route new tasks back to the legacy path only after draining or explicitly reconciling active attempts. Never run both paths as writers for one task.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 27
P06 Supported client entry points
27
Developers use Agentmux from their preferred supported client.
Work
Package CLI/MCP integrations for selected hosts.
Declare control, event, resume and hook capabilities.
Acceptance gate
Actual-host reference workflows pass.
Unsupported capabilities remain explicit.
P06-AC01 through P06-AC04
Owner: Integrations + developer experience
Notes: PROPOSED PHASE. Full authoritative phase definition follows, including all acceptance criteria, verification, evidence and rollback. No criteria are claimed passed.
P06: Agent-client entry points and portable tooling
Status: proposed
Outcome: Developers use Agentmux from their preferred supported client.
Accountable function: Integrations + developer experience
Relative size: L (complexity, not calendar duration)
Dependencies: P05
Work packages
1. Provide stable CLI and MCP interfaces generated from declared command contracts, with discoverable resources and error semantics.
2. Package and test integrations for Claude Code, Codex CLI, Pi, and Claude Desktop using each host's documented capabilities.
3. Distinguish external client sessions submitting work from Agentmux-managed worker sessions. Publish coverage for events, controls, resume, hooks, and compaction.
4. Add setup, credential references, diagnostics, install checks, and client-specific documentation without silently replacing user configuration.
5. Inventory and qualify existing Grok/provider authentication methods and any Bedrock compatibility path. Migrate GitHub and Jira/Confluence workflows as tool plugins with explicit writes and credentials.
Acceptance criteria
P06-AC01: Each supported client can submit a task, inspect progress/evidence, participate in required approvals, and retrieve the result.
P06-AC02: Unsupported event capture, cancellation, or compaction reports an explicit capability limit instead of simulating success.
P06-AC03: Closing the originating client or observer does not duplicate or implicitly terminate durable work.
P06-AC04: Fresh-user install and uninstall preserve unrelated client settings and secrets.
Verification
1. Execute the same reference workflow on every pinned client version in the support matrix.
2. Test reconnect, authentication expiry, missing tool, malformed MCP request, and client shutdown.
3. Review provider commercial integration terms before promising a supported paid distribution.
Required evidence
- Actual-host compatibility matrix
- CLI/MCP reference and setup guides
- Per-client workflow results
Rollback / containment: Disable only the affected adapter and preserve the underlying task state and alternate CLI access.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 28
P07 AG-UI and Atomic Design
28
Authorized users can understand work across agents, projects, and hubs.
Work
Project authorized NATS state into CopilotKit.
Implement views, replay, domain slots and accessibility.
Acceptance gate
Viewers converge after reconnect.
No cross-project leaks or duplicate execution.
P07-AC01 through P07-AC05
Owner: Frontend + interface platform
Notes: PROPOSED PHASE. Full authoritative phase definition follows, including all acceptance criteria, verification, evidence and rollback. No criteria are claimed passed.
P07: AG-UI dashboard and Atomic Design
Status: proposed
Outcome: Authorized users can understand work across agents, projects, and hubs.
Accountable function: Frontend + interface platform
Relative size: L (complexity, not calendar duration)
Dependencies: P06
Work packages
1. Build a NATS-facing interface plugin that converts authorized state/events into a pinned AG-UI contract for CopilotKit.
2. Implement plans, tasks/boards, runs/attempts, agents/hubs, tool activity, agent conversations, evidence/artifacts, decisions/costs, settings, and domain contribution slots.
3. Use snapshots, ordered deltas, stable IDs/cursors, resynchronization, redaction, and explicit unknown/stale state.
4. Use atoms, molecules, organisms, templates, and feature/page composition. Implement keyboard, contrast, accessible names, empty/error/offline states.
5. Include approvals and run controls only to the approved scope. Commands always return to their authoritative owner over NATS.
Acceptance criteria
P07-AC01: Refresh, reconnect, duplicate events, delayed events, and history gaps converge to the same authorized view without starting work.
P07-AC02: An unauthorized user cannot access another project's snapshots, streams, conversation, or artifact by guessing an ID.
P07-AC03: Every displayed completion or cancellation state distinguishes worker output from accepted/confirmed state.
P07-AC04: Domain UI contributions use versioned registered components. Core views remain usable when an optional plugin fails.
P07-AC05: Reusable component boundaries and accessibility checks pass for all launch views.
Verification
1. Run multi-viewer browser tests, revoked-session tests, stream replay, and network interruptions.
2. Compare UI snapshots to authoritative records after each failure scenario.
3. Run component dependency checks, keyboard/screen-reader review, and visual regression tests.
Required evidence
- AG-UI event mapping
- UI extension and accessibility reports
- Dashboard before/after demonstration
Rollback / containment: Retain CLI access and pin the prior interface/UI version. A UI rollback cannot roll back task ownership.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 29
P08 Jev decision services
29
Plugins request bounded semantic advice with traceable evidence and safe fallback.
Work
Implement scoped definitions, cache, budgets and fallback.
Compare semantic quality and total workflow cost.
Acceptance gate
Jev cannot create authority.
Holdout and cost gates pass per definition.
P08-AC01 through P08-AC05
Owner: Decision platform + evaluation
Notes: PROPOSED PHASE. Full authoritative phase definition follows, including all acceptance criteria, verification, evidence and rollback. No criteria are claimed passed.
P08: Jev decision services and measured efficiency
Status: proposed
Outcome: Plugins request bounded semantic advice with traceable evidence and safe fallback.
Accountable function: Decision platform + evaluation
Relative size: L (complexity, not calendar duration)
Dependencies: P07
Work packages
1. Implement a language-neutral decision service with optional Jev provider, versioned definitions/rubrics/schemas, scoped NATS requests, cache, budgets, cancellation, and evidence ledger.
2. Check exact rules and data-export authority before hosted inference. Distinguish known answer, abstention, partial evidence, unavailable provider, and ambiguous billing.
3. Support the eight reusable decision families and contributed definitions. Start in shadow/advisory mode for capability discovery, evidence selection, failure triage, and review.
4. Preserve exact source IDs/spans, required facts, contrary evidence, and context-expansion routes. Mandatory events bypass relevance filters.
5. Measure downstream tokens, provider costs, prompt-cache effects, latency, retries, rework, and accepted outcomes against a baseline.
Acceptance criteria
P08-AC01: Boot and core orchestration still work when Jev is disabled or unreachable, using documented fallbacks.
P08-AC02: Jev cannot grant authority, mutate kernel state, invent tool success, transfer task ownership, or accept a result.
P08-AC03: Cache keys bind tenant, scope, source/version, definition/model, and policy. Revoked sharing cannot return a cached restricted result.
P08-AC04: All calls obey size/time/budget limits and account for failed/uncertain attempts. Replay of stored annotations makes no new paid call.
P08-AC05: Each enabled definition passes its own labeled holdout criteria and workflow non-regression threshold before promotion.
Verification
1. Run the existing synthetic examples and 44-case policy illustration as historical inputs, then extend with real service and NATS tests.
2. Evaluate with provider mocks for mechanics, separately with capped live calls for semantic quality after local token configuration and budget approval.
3. Compare deterministic baseline, Jev tools only, and tools plus skills on equivalent fresh tasks.
Required evidence
- Decision contracts and policy ledger
- Definition-specific scorecards
- Cost per accepted outcome and fallback report
Rollback / containment: Disable a definition or provider and use the deterministic/manual fallback. Retain audit/evaluation history.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 30
P09 Portable Jev and first skills
30
The same Jev capabilities improve supported clients with host-specific packaging.
Work
Package tools and evaluate triggers and obligations.
Qualify local modes. Remote modes wait for P10.
Acceptance gate
Whole-suite near misses pass.
Actual-host, semantic and cost evidence support defaults.
P09-AC01 through P09-AC05
Owner: Skills + client integrations
Notes: PROPOSED PHASE. Full authoritative phase definition follows, including all acceptance criteria, verification, evidence and rollback. No criteria are claimed passed.
P09: Portable Jev plugin and first skill wave
Status: proposed
Outcome: The same Jev capabilities improve supported clients with host-specific packaging.
Accountable function: Skills + client integrations
Relative size: L (complexity, not calendar duration)
Dependencies: P08
Work packages
1. Build one shared Jev CLI/MCP runtime and portable skill content with separate Claude, Codex, Pi, and Desktop packaging.
2. Keep standalone Jev usable without Agentmux or NATS. In Agentmux mode route decision requests through scoped hub services.
3. Create the proposed first general skill wave: setup, classify, scout, context, triage, review, author, and eval.
4. Create the first Agentmux wave: prepare-worker, delegate, inspect-hub, and review-results. Qualify local-hub behavior in P09 and keep remote-hub modes disabled until P10 actual-hub acceptance. Keep final delegation authorization with platform owners.
5. Use skill-creator to draft, run paired behavioral and trigger tests, review results, revise, and qualify untouched holdout cases.
Acceptance criteria
P09-AC01: All first-wave skills have a clear trigger, declared input/output, real use case, error/fallback behavior, and evaluation fixtures.
P09-AC02: Whole-suite near-miss tests show skills do not compete unnecessarily or trigger a broad ask-everything path.
P09-AC03: Every claimed host capability passes on that actual host. Unsupported hooks/compaction are declared.
P09-AC04: Skills preserve counterevidence and required obligations and cannot override system permissions or invent authority.
P09-AC05: Live semantic and end-to-end cost gates pass before the corresponding skill is enabled by default.
Verification
1. Run approximately 20 positive/near-miss trigger prompts per skill and representative task pairs plus shared boundary cases.
2. Use independent review and separate tuning/validation/release sets.
3. Measure skill discovery metadata overhead, context cost, accuracy, and accepted outcomes across hosts.
Required evidence
- Host packages and skill catalog
- Paired skill-creator evaluation reports
- Cross-host conformance and release holdout
Rollback / containment: Disable or uninstall the specific skill/package, preserve user config, and retain CLI/MCP access where independently qualified.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 31
P10 Connected hubs and leaf nodes
31
Independent teams share authorized work while retaining their own authority.
Work
Delegate across organizations and qualify remote skills.
Test partitions, stale restores and retention gaps.
Acceptance gate
Origin owns acceptance.
Lost acceptance replies and outages never cause blind redispatch.
P10-AC01 through P10-AC06
Owner: Federation + security + reliability
Notes: PROPOSED PHASE. Full authoritative phase definition follows, including all acceptance criteria, verification, evidence and rollback. No criteria are claimed passed.
P10: Connected hubs, leaf nodes, and cross-organization work
Status: proposed
Outcome: Independent teams share authorized work while retaining their own authority.
Accountable function: Federation + security + reliability
Relative size: XL (complexity, not calendar duration)
Dependencies: P09
Work packages
1. Implement scoped trust agreements, node/peer enrollment, NATS leaf topology, independent JetStream domains where needed, and selective sharing/replication.
2. Publish authorized capabilities and capacity. Filter deterministic eligibility before optional Jev suitability scoring and revalidate at offer time.
3. Implement durable offer, acceptance, reservation, execution reporting, result submission, origin acceptance, reconciliation, revocation, and explicit reassignment.
4. Support work/context/artifacts/code/findings/messages/board projections with authenticated provenance, digests, visibility, and retention.
5. Add automatic receiving-hub acceptance inside approved rules, pending human approval for review-required work, and rejection for hard-denied work. Enforce any onward delegation/export separately.
6. Qualify and enable the remote-hub modes of P09 delegate, inspect-hub, and review-results skills on real connected hubs and supported clients. Their earlier local qualification does not count as federation evidence.
Acceptance criteria
P10-AC01: Same-organization and cross-organization reference workflows both finish with origin-owned result acceptance.
P10-AC02: Accepted work stays reserved while disconnected. Missing acceptance acknowledgment remains ambiguous until reconciled, never automatically redispatched.
P10-AC03: Duplicate offer/result delivery creates one delegation/attempt outcome. Wrong executor, project, repository, or task version is rejected. Stale grants cannot authorize new effects. Authenticated historical results from previously authorized reserved work are retained for reconciliation or quarantine when current policy requires it; grant expiry cannot erase the obligation or its evidence.
P10-AC04: Unauthorized accounts cannot subscribe to private project subjects or fetch protected artifacts. Transitive hub connectivity grants no access.
P10-AC05: Reconnect recovers progress/results and durable revocations. A stop request is not reported as execution stopped until confirmed or clearly unknown.
P10-AC06: A leaf outage and independent local persistence produce the agreed offline behavior without treating broker connectivity as shared ownership.
Verification
1. Run at least three hubs and two independently administered organizations with real accounts/leaf links and isolated stores.
2. Inject partitions before/after offer acceptance, drop replies, duplicate deliveries, restart hubs, expire/revoke grants, and alter task versions.
3. Exercise explicit cancel/reassign with a possibly running old worker and document unavoidable external-effect uncertainty.
4. Snapshot the origin before a remote acceptance, let the receiver accept and continue, restore that older origin snapshot, and require reconciliation before overlapping admission. Verify one reservation and no duplicate execution.
5. Disconnect beyond configured stream-retention and deduplication horizons using short test limits, then prune, restart, and reconnect. Require gap detection, snapshot/reconciliation or explicit intervention, preserved reservations, and no duplicate effects.
Required evidence
- Federation state-machine and authority tests
- Partition/reconciliation matrix
- Cross-organization demo with auditable evidence
Rollback / containment: Disable new links and stop new offers. Preserve reservations and reconcile accepted work before returning to a prior federation version.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 32
P11 Industrial packages
32
Industrial workflows extend Agentmux through the same contracts as other domains.
Work
Port domain and vendor behavior through plugin contracts.
Declare host/tool support and mutation safeguards.
Acceptance gate
Selected reference workflow passes.
Simulator claims stay separate from hardware qualification.
P11-AC01 through P11-AC05
Owner: Domain engineering + plugin SDK
Notes: PROPOSED PHASE. Full authoritative phase definition follows, including all acceptance criteria, verification, evidence and rollback. No criteria are claimed passed.
P11: Industrial and vendor extension packages
Status: proposed
Outcome: Industrial workflows extend Agentmux through the same contracts as other domains.
Accountable function: Domain engineering + plugin SDK
Relative size: XL (complexity, not calendar duration)
Dependencies: P10
Work packages
1. Package industrial orchestration guidance, tools, schemas, UI renderers, and skills with explicitly independent or parent-owned children.
2. Migrate current Modbus, MQTT, network discovery, PROFINET snapshot/DCP, passive BOOTP, EtherNet/IP/Logix, ADS, EtherCAT diagnostics, CODESYS runtime tooling, PCAP analysis, and existing engineering wrappers to declared capability plugins.
3. Define CODESYS, Siemens, Rockwell, and related vendor integration slices with actual licensed tool/OS/hardware prerequisites and test environments.
4. Add engineering build/migration/evidence skills and Jev definitions for diagnostics and source-preserving comparisons.
5. Implement read/simulation-first reference workflows and per-action permissions for equipment changes. Resolve any Windows-native execution host arrangement explicitly.
6. Inventory existing PCM600/ABB-related privilege hooks as integration requirements, preserving target/action confirmation and audit. Do not infer a complete vendor adapter from the existence of a guard hook.
Acceptance criteria
P11-AC01: A selected industrial workflow completes through client, orchestration, tool plugin, evidence, and dashboard without kernel or generic task-model changes.
P11-AC02: Standalone and nested installation of selected domain children behave as declared.
P11-AC03: Every migrated existing integration has a parity/deprecation record, tested tool/platform matrix, and explicit missing capability status.
P11-AC04: Equipment writes require the correct target/action/operation grant and any applicable human approval at the owning tool endpoint.
P11-AC05: A vendor adapter passes with the actual required tool or a clearly labeled simulator. Simulated success is never sold as hardware qualification.
Verification
1. Use protocol simulators and recorded fixtures, then controlled hardware/vendor environments for supported claims.
2. Test wrong device/project/version, timeout, partial writes, lost replies, credential failure, and disconnected grants.
3. Demonstrate missing Windows-native prerequisites as an actionable unsupported environment, not silent fallback.
Required evidence
- Domain package and vendor compatibility matrix
- Industrial workflow and permission report
- Protocol parity and hardware qualification records
Rollback / containment: Disable the affected domain capability and drain sessions. Preserve device-state uncertainty and do not automatically reverse external equipment effects.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 33
P12 Production qualification
33
Customers can install, operate, recover, and support the complete launch product.
Work
Qualify install, upgrades, support and recovery.
Prove capacity, two-organization work and release coverage.
Acceptance gate
All launch evidence matches the candidate.
Ryan authorizes merge/release after review with Nick.
P12-AC01 through P12-AC05
Owner: Release + operations + product
Notes: PROPOSED PHASE. Full authoritative phase definition follows, including all acceptance criteria, verification, evidence and rollback. No criteria are claimed passed.
P12: Production hardening and first sellable release
Status: proposed
Outcome: Customers can install, operate, recover, and support the complete launch product.
Accountable function: Release + operations + product
Relative size: XL (complexity, not calendar duration)
Dependencies: P11
Work packages
1. Finish signed/reproducible distributions, dependency locks/SBOM, versioned configuration, upgrade/rollback, package verification, and support diagnostics.
2. Complete self-hosted topology guides, backup/restore drills, durable retention/pruning, quotas/fairness, monitoring, alerts, incident procedures, and consented telemetry.
3. Validate launch performance/capacity profiles, broker/storage failure recovery, long-running work, and cross-organization safety.
4. Finish onboarding, documentation, reference plugins, accessibility, support ownership, commercial licensing/provider eligibility, and pilot feedback.
5. Rehearse migration from v0.32.0 across board/run/hub/federation state, credentials, worktrees, and integrations. Keep an explicit compatibility retirement plan.
6. Restore an origin hub while a receiver continues accepted work, reconcile outstanding reservations before admitting replacements, test backup-name collisions, and preserve WSL database filesystem requirements.
Acceptance criteria
P12-AC01: Every launch requirement is linked to passing evidence for the exact release candidate. Critical correctness/security defects are closed.
P12-AC02: A new developer installs and completes the reference task using only published docs on every supported platform.
P12-AC03: A team administrator enrolls two organizations, shares a scoped project, delegates work, survives a partition, and restores a backup.
P12-AC04: The approved capacity/SLO targets and recovery drill pass without losing acknowledged durable records within the tested fault model.
P12-AC05: Ryan reviews the release evidence with Nick and explicitly authorizes merge/release. Passing automation alone cannot merge this branch.
Verification
1. Run the complete release matrix, independent security review, load/soak tests, upgrade/restore rehearsal, and pilot acceptance.
2. Compare evidence manifests to the exact candidate digest and invalidate stale results after material changes.
3. Review support and commercial readiness with accountable owners.
Required evidence
- Release readiness dossier
- Pilot and migration acceptance
- Signed merge/release decision
Rollback / containment: Use rehearsed backup/restore and version compatibility procedures. Stop new work where safe downgrade is impossible; reconcile in-flight tasks first.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 34
P13 Remaining Jev and skills
34
Every remaining research proposal receives a measured implementation decision.
Work
Evaluate remaining catalog ideas in bounded batches.
Qualify advanced context and supported compaction controls.
Acceptance gate
Every proposal retains a disposition.
Quality and full economics support each activation.
P13-AC01 through P13-AC04
Owner: Decision platform + domain owners
Notes: PROPOSED PHASE. Full authoritative phase definition follows, including all acceptance criteria, verification, evidence and rollback. No criteria are claimed passed.
P13: Remaining Jev catalog and skill expansion
Status: proposed
Outcome: Every remaining research proposal receives a measured implementation decision.
Accountable function: Decision platform + domain owners
Relative size: L–XL per batch (complexity, not calendar duration)
Dependencies: P12
Work packages
1. Implement the complete remaining catalog in bounded batches using the coverage appendix, without duplicating overlapping video and original use cases.
2. Complete general extract, compare, checkpoint, integrate, and optimize skills plus remaining Agentmux planning, coordination, diagnosis, knowledge, plugin review, and policy-tuning skills.
3. Expand temporary bounded questions, semantic inventories, federated source inspection, compaction/retention controls, what-if replay, fidelity review, bilateral contract interpretation, and opportunity scorecards.
4. Promote only qualified definitions. Record rejected or deferred cases with evidence, reasons, owner, and next review point.
Acceptance criteria
P13-AC01: All 88 original uses, 14 video additions, four enablers, and 26 skills retain a traceable disposition and owning phase.
P13-AC02: Each batch passes schema, access, failure, semantic holdout, host-capability, and end-to-end economic gates.
P13-AC03: Compaction preserves mandatory obligations and active evidence and runs only on supported hosts.
P13-AC04: No savings claim relies only on shortened context or a provider's confidence score. Outcome quality and total cost meet approved thresholds.
Verification
1. Repeat the P08/P09 evaluation protocol per changed definition/skill and representative combined workflows.
2. Use stored factors for policy-only replay and record when a fresh inference is necessary.
3. Run regression tests for cache isolation, missing evidence, mandatory messages, provider failure, and decision drift.
Required evidence
- Catalog disposition register
- Per-batch holdout and economics
- Complete skill-suite release matrix
Rollback / containment: Independently disable definitions/skills and return to the prior pinned set while preserving all evidence.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 35
P14 Sandboxed plugins
35
Untrusted third-party plugins gain a tested containment option.
Work
Define and enforce per-platform containment profiles.
Retain compatible contracts and explicit trusted exceptions.
Acceptance gate
Adversarial escape tests pass.
Only qualified profiles claim untrusted-plugin support.
P14-AC01 through P14-AC04
Owner: Security + plugin platform
Notes: PROPOSED PHASE. Full authoritative phase definition follows, including all acceptance criteria, verification, evidence and rollback. No criteria are claimed passed.
P14: Sandboxed plugins and ecosystem expansion
Status: proposed
Outcome: Untrusted third-party plugins gain a tested containment option.
Accountable function: Security + plugin platform
Relative size: XL (complexity, not calendar duration)
Dependencies: P13
Work packages
1. Choose and threat-model isolated execution profiles, process/container/WASM options, host brokers, and platform limitations against actual plugin needs.
2. Enforce declared filesystem/network/process/device access, secret isolation, quotas, termination, and package provenance at runtime.
3. Qualify UI contribution isolation and publisher/distribution controls before enabling a public plugin ecosystem.
4. Retain trusted native profiles only with clear administrator choice. Assess future hosted service and native Windows as separate product decisions.
Acceptance criteria
P14-AC01: Adversarial plugins fail to escape their declared profile or access unauthorized host/team data in the supported threat model.
P14-AC02: Sandboxed and trusted implementations pass the same language-neutral domain contract tests.
P14-AC03: Required native/device integrations declare and enforce narrower support or an explicitly trusted execution host.
P14-AC04: Security review and per-platform tests pass before claiming untrusted-plugin support. Marketplace availability requires this gate or a clearly restricted trusted catalog.
Verification
1. Run exploit-oriented confinement, resource exhaustion, cross-tenant, lifecycle, dependency, and upgrade tests on each supported profile.
2. Review residual risk and performance/compatibility effects with independent security expertise.
3. Re-run representative local, team, federation, UI, and industrial workflows.
Required evidence
- Sandbox threat model and test report
- Profile compatibility matrix
- Ecosystem launch decision
Rollback / containment: Disable new untrusted profiles/packages and preserve the prior trusted-only support promise.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 36
Proposed capacity and responsiveness
36
Profile | Proposed workload | Purpose
Solo | 1 user, 2 projects, 4 attempts | Local overhead
Team | 20 users, 10 projects, 40 attempts | Isolation and contention
Federation | 3 hubs, 2 organizations | Partition recovery
Growth benchmark | 200 users, 10 hubs, 400 attempts | Find later bottlenecks
Starting targets for review
Metadata p95 <250 ms Dashboard update ≤2 s 10,000-event replay ≤5 s
Notes: All numbers are reviewable proposed test profiles, not measured capacity or service commitments. Plan section 8: solo 1 user/2 projects/4 attempts; team 20 users/10 projects/40 attempts; federation 3 hubs/2 organizations/up to 40 attempts per hub; growth 200 users/10 hubs/up to 400 overall. Proposed p95 metadata <250ms, UI <=2s after owner record, 10,000-event replay <=5s, warm-broker readiness <=10s, prepared setup <=15min after tools/accounts. Approve hardware, payloads, latency, retention and variance before measurement. RPO/RTO remain explicit choices.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 37
Verification across real failure boundaries
37
Mechanics
Schema, identity, replay, transaction boundaries and idempotency
Actual environments
Pinned client versions, macOS/Linux/WSL, real NATS and browser recovery
Semantic outcomes
Untouched task cases, independent labels, complete cost and rework
Operations
Partition, revocation, disk pressure, backup restore and migration rollback
Notes: This slide describes future test obligations. The companion verification-matrix.md/json records 41 failure scenarios. Prior selected baseline suites and offline Jev policy/schema examples remain historical evidence, not future platform passes. Require unit/contract tests, actual broker integration, actual client hosts, cross-tenant negative tests, fault injection, browser replay/accessibility, restore drills, capped live semantics after approval and separately authorized hardware qualification.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/.codex/visualizations/2026/10/09/01a11e6d-8b51-7ec1-962b-bac33576c294/agentmux-repository-analysis.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/verification-matrix.md

## Slide 38
Open decisions and delivery risks
38
Decision | Review needed before
Proof workflow and dashboard commands | P00 exit
Runtime, SDKs, storage and account layout | P01–P04 implementation
Client/vendor versions and commercial terms | Supported integration claims
Capacity, recovery, staffing and dates | Release promises
Jev data policy, budgets and thresholds | Capped live evaluation
Risks concentrate in bootstrap, distributed authority, client coverage and active-work migration.
Notes: These choices remain open in implementation plan section 2. Concrete recommendations make the plan reviewable without asserting acceptance. No schedule can be promised without staffing, proof spikes and actual client/vendor integration qualification. Existing accepted authority, kernel, NATS and platform boundaries persist while resolving details.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json

## Slide 39
Review and authorization
39
Resolve P00 choices
Approve or revise the phase sequence and proposed targets
Name gate reviewers and record the accepted plan revision
Implementation starts only after Ryan’s explicit authorization
Planning is ready for review. Repository governance remains blocked
until approved P01 correctness repairs pass.
Notes: Proposed next action: Ryan and Nick review the plan and criteria, resolve P00 choices, approve/revise first-release split and targets, name reviewers and record approved revision. Ryan explicitly authorizes implementation. Later merge/release is a separate decision after review. This deck and current work do not authorize product implementation. Planning is ready for review, while the repository governance gate remains blocked by inherited correctness findings until approved P01 repairs and regressions close them. Presentation package validation is separate from repository governance and product acceptance.
Sources:
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/implementation-plan.md
C:/Users/RyanHelms/GitHub/agentmux/docs/planning/2026-10-09/phases.json
C:/Users/RyanHelms/GitHub/agentmux/.bytedesk/design-patterns/review.json